## Sheet1
DeleteFlag | Type | Log Item # | ATA # | Description | Corrective Action | Discrepancy # | Action | Status | Source Task/Discrep. # | Source Tracking # | Work Center # | Sign Off Status | Contract Classification | Category | Exe. Phase | Exec. Category | Part Required? | Corrosion Related? | Major Item? | Repeat? | Part # | Serial # | Position Code | Part Description | Radio Communication | Reported By | Reported Date | Mech Req? | Mech Sign Off | Mech Skill # | Insp Req? | Insp Sign Off | Insp Skill # | RII Req? | RII Sign Off | RII Skill # | Addl. Sign Off | Add New Sign Off Comments | Previous Sign Off Comments | Planned Start Date | Planned End Date | Est. Man Hrs. | Actual Start Date | Actual End Date | Actual Man Hrs. | Seq # | Tracking # | Source Tracking # | Hold Status | Estimation Status | File Name | Skill # | Zone # | Work Area # | Deferral FH | Deferral FC | Deferral Parameter | Deferral Value | Deferral Calendar Value | Deferral Calendar | Deferral Item # | Deferral Type | Reason for Deferral | Auth. Ref. # | Message Center
No | MIREP | HMV23/000059/0923/1 | 53 | 1. DURING INSPECTION OBERVED LH WING SLATE #01, TRACK#02 ,#03, #04 UPPER BULB SEAL DAMAGE.SAME TO BE REPLACED. 2. DURING INSPECTION OBSERVED SLAT#02 TRACK #5 PLATE DAMAGE.SAME TO BE REPLACED. | 1. CARRIED OUT INSTALLATION OF LH WING SLAT #01 TRACK # 02 #03 #04 UPPER BULB SEAL AS PER STANDARD PRACTICES 20-21-11-911-001-A, REV 72, DT-01 AUG 2023.SECURITY OF INSTALLATION CHECK FOUND SATISFACTORY. 2.CARRIED OUT INSTALLATION OF LH WING SLAT #2,TRACK #05 PLATE AS PER STANDARD PRACTICES 20-21-11-911-001-A, REV 72, DT-01 AUG 2023.SECURITY OF INSTALLATION CHECK FOUND SATISFACTORY. | HMV23/000059/0923/1 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | DISC-INTERNAL TASK | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1085 | 2023-09-25 08:37 | Yes | MR1085 | B1 | Yes | MR1085 | B1 | No | [5 empty] | 2023-09-19 10:40 | 2023-09-27 17:05 | 4 | 2023-09-25 12:35 | 2023-09-27 17:07 | 4 | 179 | 179 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/2 | 34 | DURING ARRIVAL INSPECTION CHECK FOUND FAILURE MESSAGE IN PFR " NO ADF 1 DATA (INTM) ". | CARRIED OUT TROUBLESHOOTING IAW TSM TASK 31-32-00-810-955-A REV 72 DATED 01 AUG 2023 AND TSM TASK 31-32-00-810-827-A REV 72 DATED 01 AUG 2023. CARRIED OUT PROCEDURE FOR THE CLASS 3 FAULTS READING IAW AMM TASK 31-32-00-869-002-A REV 72 DATED 01 AUG 2023. FOUND SATISFACTORY. | HMV23/000059/0923/2 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Not Required | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-25 08:40 | No |  |  | No |  |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 4 | 2023-09-27 17:17 | 2023-09-28 12:52 | 4 | 180 | 180 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/3 | 23 | DURING ARRIVAL INSPECTION FOUND STATIC DISCHARGERS DAMAGED AT LOCATION : 1) LH HORZ STAB TYPE A DISCHARGER QTY# 2 & TYPE B DISCHARGER QTY#3 2) RH HORZ STAB TYPE A DISCHARGER QTY#1 3)VERTICAL STABILISER TYPE A DISCHARGER QTY 01 & TYPE B DISCHARGER QTY 02. | STATIC DISCHARGERS REPLACED AT FOLLOWING LOCATIONS AS PER AMM 23-61-41-000-001-A AND 23-61-41-400-001-A REV 72, DT 01/08/2023. 1) LH HORZ STAB TYPE A DISCHARGER QTY# 2 & TYPE B DISCHARGER QTY#3 2) RH HORZ STAB TYPE A DISCHARGER QTY#1 3)VERTICAL STABILISER TYPE A DISCHARGER QTY 01 & TYPE B DISCHARGER QTY 02. POST INSTALLATION OF NEW STATIC DISCHARGERS RESISTANCE TEST CARRIED OUT AS PER AMM 23-61-00-200-001 REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. | HMV23/000059/0923/3 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-25 08:59 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 5 | 2023-09-26 08:00 | 2023-09-28 15:11 | 5 | 181 | 181 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/4 | 53 | DURING ARRIVAL CHECK FOUND SERVICE LIGHT LAMP INOP AT FOLLOWING LOCATION 1.103VU BATTERY COMPARMENT LAMP FIN: 8LS QTY#1,. 2. REFUEL/DEFUEL CONTROL PANEL FLOODLIGHT LAMP FIN: 32QU. | 1. CARRIED OUT REPLACEMENT OF SERVICE LIGHT LAMP AT LOCATION 103VU BATTERY RH AVIONICS COMPARTMEN FIN: 8LS QTY#1 IAW AMM TASK 33-35-11-000-002-A/AMM TASK 33-35-11-400-002-A REV 72 DTD 01 AUG 2023. POST INSTALLATION OPERATIONAL TEST OF AVIONICS COMPARTMENT LIGHTING CARRIED OUT IAW AMM TASK 33-35-00-720 -001 REV 72 01 AUG 2023. FOUND SATISFACTORY. 2. CARRIED OUT REPLACEMENT OF FLOOD LIGHT LAMP QTY#1 FIN: 32QU IAW AMM TASK 28-25-54-000-001-A / AMM TASK 28-25-54-400-001-A REV 72 DTD 01 AUG 2023. POST INSTALLATION TEST CARRIED OUT IAW AMM TASK 28-25-54-710-050-A REV 72 DTD 01 AUG 2023. FOUND SATISFACTORY. | HMV23/000059/0923/4 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Not Required | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-25 09:07 | No |  |  | No |  |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 6 | 2023-09-26 09:57 | 2023-09-28 14:09 | 3 | 182 | 182 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/5 | 53 | DURING ARRIVAL INSPECTION , OBSERVED FOLLOWINS DICREPANCIES. 1) RH SIDE WING NO#1 SLAT, NO.3 TRACK SQURE SEAL UPPER BULB SEAL DEGRADED. 2) RH SIIDE WING SLAT NO#5 OUT BOARD WEATHER SEAL ERODED. SAME TO BE REPLACED. | 1) RH SIDE WING NO#1 SLAT, NO.3 TRACK SQURE SEAL UPPER BULB SEAL REPLACED AS PER AMM 20-21-11-911-001-A, REV 72, DT-01 AUG 2023.SECURITY OF INSTALLATION CHECK FOUND SATISFACTORY. 2) RH WING SLAT #5 OUT BOARD WEATHER SEAL REPLACED AS PER AMM 20-21-11-911-001-A, REV 72, DT-01 AUG 2023.SECURITY OF INSTALLATION CHECK FOUND SATISFACTORY. | HMV23/000059/0923/5 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1089 | 2023-09-25 09:36 | Yes | mr0001 |  | Yes | mr0001 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 3 | 2023-09-25 10:02 | 2023-09-29 10:36 | 0 | 183 | 183 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/6 | 53 | DURING INSPECTION FOUND FOLLOWING FORWARD CARGO FLOOR PANEL DAMAGED , TO BE FABRICATED/REPLACED 131EF P/N D5367521000000 131FF P/N D5367400800000 131BF P/N D5367401200000 131JF P/N D5367400600000 | 1) FORWARD CARGO FLOOR BOARD HARDWARE REPLACED IRC HMV23/000055/0923/6 FOR DETAILS 2) FWD CARGO COMPARTMENT AFT PARTITION PANELS HARDWARE INSTALLED AS PER AMM TASK 25-54-12-400-001-A REV 72 DATED 01 AUG 2023 | HMV23/000059/0923/6 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-25 09:47 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 20 | 2023-09-26 06:41 | 2023-09-28 12:45 | 15 | 184 | 184 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/7 | 53 | DURING INSPECTION FOUND FOLLOWING AFT CARGO FLOOR PANEL DAMAGED , TO BE FABRICATED/REPLACED 151LF P/N D5367521106800 151GF P/N D5367521100400 151DF P/N D5367521100200 151EF P/N D5367402100000 | CARRIED OUT REMOVAL OF AFT CARGO FLOOR PANELS AS PER AMM TASK 53-42-14-000-001-A REV 72 DATED 01 AUG 2023 CARRIED OUT INSTALLATION OF AFT CARGO FLOOR PANELS AS PER AMM TASK 53-42-14-400-001-A REV 72 DATED 01 AUG 2023 . REFER FOLLOWING CWO FOR FABRICATION 151LF P/N D5367521106800 CWO23/000419/0923 151GF P/N D5367521100400 CWO23/000420/0923 151DF P/N D5367521100200 CWO23/000421/0923 151EF P/N D5367402100000 CWO23/000422/0923 | HMV23/000059/0923/7 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-25 09:49 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-25 09:49 | 2023-09-25 10:49 | 20 | 2023-09-25 16:25 | 2023-09-28 12:42 | 20 | 185 | 185 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/8 | 53 | DURING ARRIVAL INSPECTION OF FORWARD CARGO , FOUND HARDWARE DAMAGED/MISSING | 1) FORWARD CARGO FLOOR BOARD HARDWARE REPLACED IRC HMV23/000055/0923/6 FOR DETAILS 2) FWD CARGO COMPARTMENT AFT PARTITION PANELS HARDWARE INSTALLED AS PER AMM TASK 25-54-12-400-001-A REV 72 DATED 01 AUG 2023 | HMV23/000059/0923/8 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-25 09:52 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-25 09:52 | 2023-09-25 10:52 | 6 | 2023-09-26 07:58 | 2023-09-28 15:34 | 5 | 186 | 186 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/9 | 53 | DURING ARRIVAL INSPECTION OF AFT CARGO , FOUND 1) CARGO SECTION HOSE MISSING/ DAMAGED 2) FOUND HARDWARE DAMAGED/MISSING | 1) AFT CARGO SECTION HOSE AND AFT CARGO FLOOR BOARD HARDWARE REPLACED REFER IRC HMV23/000055/0923/7 FOR DETAILS . 2) AFT CARGO SIDEWALL HARDWARE INSTALLED AS PER TASK 25-55-11-400-003-A REV 72 DATED 01 AUG 2023 . 3) AFT CARGO COMPARTMENT CEILING PANELS HARDWARE INSTALLED AS PER AMM TASK 25-55-11-400-002-A REV 72 DATED 01 AUG 2023 | HMV23/000059/0923/9 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-25 09:53 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-25 09:53 | 2023-09-25 10:53 | 5 | 2023-09-26 10:01 | 2023-09-27 11:49 | 7 | 187 | 187 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/10 | 53 | DURING OPPORTUNITY INSPECTION FOUND BELLY PANEL HARDWARE DAMAGED/MISSING | BELLY PANEL HARDWARE REPLACED AS PER AMM 20-21-00 REV 72 DATED 01 AUG 2023 | HMV23/000059/0923/10 | Close | Closed | 215222-01-1 (LH) | 16 | LINE 1A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-25 09:58 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-25 09:58 | 2023-09-25 10:58 | 5 | 2023-09-26 12:15 | 2023-09-27 10:58 | 2 | 188 | 188 |  | Hold | Released Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/11 | 53 | DURING INSPECTION FOUND PISTON TYPE DRAIN VALVES FOUND DAMAGED/ DEFECTIVE VALVE P/N ABS0341-2-01 | CARRIED OUT REPLACEMENT OF THE DRAIN VALVES AS AMM TASK 53-49-21-000-001-A/ TASK 53-49-21-400-001-A , REV 72 , DATED 01 AUG 2023 VALVE P/N ABS0341-2-01 | HMV23/000059/0923/11 | Close | Closed | 531900-03-1 | 123 | LINE 1A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-25 10:37 | Yes | mr1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-25 10:37 | 2023-09-25 11:37 | 5 | 2023-09-26 10:33 | 2023-09-26 14:42 | 4 | 189 | 189 |  | Hold | Released Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/12 | 38 | DURING INSPECTION FOUND COMPRESSOR INLET FILTER BLOCKED , TO BE REPLACED | COMPRESSOR INLET FILTER REPLACED REFER MPD 384241-01-1 FOR REPLACEMENT DETAILS P/N 7006-15 | HMV23/000059/0923/12 | Close | Closed | 384241-01-1 | 106 | LINE 1A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-25 10:40 | Yes | mr1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-25 10:40 | 2023-09-25 11:40 | 2.5 | 2023-09-26 12:15 | 2023-09-26 14:44 | 3 | 190 | 190 |  | Hold | Released Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/13 | 21 | DURING OPPORTUNITY INSPECTION FOUND LH ACM ANTI ICE TUBE FOUND TORN , TO BE REPLACED P/N 3455-23 | LH ACM ANTI ICE TUBE REPLACED AS PER AMM 20-21-00 REV 72 DATED 01 AUG 2023 . PRECONDITIONING CARRIED OUT AS PER AMM 12-33-21-618-001 REV 72 DATED 01 AUG 2023 , NO LEAKS FOUND . TUBE P/N 3455-23 | HMV23/000059/0923/13 | Close | Closed | 215222-01-1 (LH) | 16 | LINE 1A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-25 11:32 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-25 11:32 | 2023-09-25 12:32 | 4 | 2023-09-25 12:42 | 2023-09-27 08:12 | 2.5 | 191 | 191 |  | Hold | Released Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/14 | 53 | TO FACILITATE THE HFEC INSPECTION ON THE DENT B/W FR9 TO FR10 ACCESS TO BE PROVIDED. | TO FACILITATE INSPECTION, OXYGEN MASK STOWAGE BOXES (10RN2 AND 10RN3) REMOVED AS PER AMM 35-12-41-000-001-A REV 72, DT 01/08/2023. POST INSPECTION SAME OXYGEN MASK STOWAGE BOXES (10RN2 AND 10RN3) INSTALLED AS PER AMM 35-12-41-400-001-A REV 72, DT 01/08/2023. POST INSTALLATION TESTS CARRIED OUT. FOUND SATISFACTORY. | HMV23/000059/0923/14 | Close | Closed | AWR23/002877/0923 | 172 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1097 | 2023-09-25 14:46 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-27 11:54 | 8 | 2023-09-27 08:12 | 2023-09-27 12:18 | 6 | 192 | 192 |  | Hold | Released Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/15 | 33 | DURING ARRIVAL CHECK FOUND EPSU BATTERIES QTY#2 FIN:10WL AND FIN: 11WL INOP. | 1. TROUBLESHOOTING CARRIED OUT IAW TSM TASK 33-51-00-810-829-A REV 72 DTD 01 AUG 2023 AND TSM TASK 33-51-00-810-855-A REV 72 DTD 01 AUG 2023 FOUND EPSU BATTERIES QTY#2 FIN:10WL AND FIN: 11WL FAULTY. 2. CARRIED OUT REMOVAL OF EPSU BATTERIES QTY#2 FIN: 10WL AND FIN: 11WL IAW AMM 33-51-38-000-002-A REV 72 DTD 01 AUG 2023. FIN: 10WL OFF PN: 3214-31 OFF SN: 874832 FIN: 11WL OFF PN: 3214-31 OFF SN: 875081 3. CARRIED OUT INSTALLATION OF NEW EPSU BATTERIES QTY#2 FIN: 10WL AND FIN: 11WL IAW AMM 33-51-38-400-002-A REV 72 DTD 01 AUG 2023. FIN: 10WL ON PN: 3214-31 ON SN: 936711 FIN: 11WL ON PN: 3214-31 ON SN: 936712 4. POST INSTALLATION OF NEW EPSU BATTERIES QTY#2 FIN: 10WL AND FIN: 11WL CARRIED OUT OPERATIONAL CHECK OF THE EPSU BY BITE CHECK IAW AMM 33-51-00-710-001-A REV 72 DTD 01 AUG 2023 AND INTERFACE AND POWER-UP TEST OF THE CABIN INTERCOMMUNICATION DATA SYSTEM (CIDS) THROUGH THE CFDS IAW AMM TASK 23-73-00-740-005-A REV 72 DTD 01 AUG 2023. FOUND SATISFACTORY. | HMV23/000059/0923/15 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Not Required | AWR |  | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-25 14:59 | No |  |  | No |  |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 5 | 2023-09-27 17:01 | 2023-09-28 15:12 | 6 | 193 | 193 |  | Hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/16 | 20 | DURING WEAR LIMIT BONDING LEADS INSPECTION CHECK FOUND BONDING LEADS DAMAGED AT LOCATION TOILET SERVICE PANEL QTY#1, WATER SERVICE PANEL QTY#2, RH MLG DOOR QTY#1, LH MLG DOOR QTY#1, LH ELEVATOR QTY#3, RH ELEVATOR QTY#1, RH WING BETWEEN SPOILER 3 AND 4 QTY#2, LH WING FLAP TRACK FAIRING NO.3 QTY#1, RH WING FLAP TRACK FAIRING NO.1 QTY#2. | CARRIED OUT REPLACEMENT OF DAMAGED BONDING LEADS WITH SERVICEABLE BONDING LEADS AT LOCATION TOILET SERVICE PANEL QTY#1 ( 0.5 MILLIOHM), WATER SERVICE PANEL QTY#2 (0.6 MILLIOHM, 0.7 MILLIOHM), RH MLG DOOR QTY#1 (0.6 MILLIOHM), LH MLG DOOR QTY#1 (0.5 MILLIOHM), LH ELEVATOR QTY#3 (0.7 MILLIOHM, 0.5 MILLIOHM, 0.6 MILLIOHM), RH ELEVATOR QTY#1 (0.6 MILLIOHM), RH WING BETWEEN SPOILER 3 AND 4 QTY#2 (0.7 MILLIOHM, 0.6 MILLIOHM), LH WING FLAP TRACK FAIRING NO.3 QTY#1 (0.5 MILLIOHM), RH WING FLAP TRACK FAIRING NO.1 QTY#2 (0.6 MILLIOHM, 0.5 MILLIOHM) IAW AMM TASK 20-28-00-912-802-A REV 72 DATED AUG 01 2023. POST INSTALLATION OF NEW BONDING LEADS BONDING TEST CARRIED OUT IAW AMM 20-28-00-869-002 REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. | HMV23/000059/0923/16 | Close | Closed | WEAR LIMITS- BONDING LEADS | 135 | LINE 1A | Not Required | DISC-ADD-SB/EO/MOD/SI/SL | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-26 07:37 | No |  |  | No |  |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 23 | 2023-09-26 07:56 | 2023-09-28 12:38 | 18 | 194 | 194 |  | Not in hold | Released Estimates | [9 empty] | Hours
No | MIREP | HMV23/000059/0923/17 | 25 | DURING INSPECTION OF PAX SEATS FOLLOWING FINDINGS OBSERVED:- 1. BAGGAGE BAR HARDWARES FOUND MISSING AT MULTIPLE LOCATIONS. 2. SEAT BELTS QTY 12 FOUND FRAYED AND WORN OUT. 3. ARM CAP QTY 1 FOUND DAMAGED. 4. SEAT FLANK FAIRINGS AND SPREADER FAIRING FOUND DAMAGED AT MULTIPLE LOCATIONS. | 1. MISSING BAGGAGE BAR HARDWARES REPLACED AS PER STANDARD PRACTICES AMM TASK 20-21-11-911-001-A, REV 72, DTD: 01-AUG-2023. 2. SEAT BELTS QTY 12 REPLACED AS PER AMM 25-21-42-400-002-A, REV 72, DTD: 01-AUG-2023. 3. SEAT ARM CAP QTY 1 REPLACED WITH NEW ONE AS PER STANDARD INDUSTRIAL PRACTICES. 4. FLANK FAIRINGS AND SPREADER FAIRINGS REPLACED AS PER STANDARD PRACTICES AMM TASK 20-21-11-911-001-A, REV 72, DTD: 01-AUG-2023. | HMV23/000059/0923/17 | Close | Closed | 252100-01-1 | 24 | LINE 1A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1097 | 2023-09-26 09:44 | Yes | MR1097 |  | Yes | MR1097 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 16 | 2023-09-28 11:31 | 2023-09-28 15:08 | 16 | 195 | 195 |  | Hold | Released Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/18 | 25 | REFER CABIN DEFECT LOG DEFERRED ITEM #14:- AFT GALLEY LATCH 414ABC DEFECTIVE. | AFT GALLEY LATCH 414ABC FOUND DEFECTIVE DUE TO GRUB SCREWS LOOSE, SAME RETIGHTENED. OPERATION CHECKED, FOUND SATISFACTORY. | HMV23/000059/0923/18 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1097 | 2023-09-26 11:05 | Yes | MR1097 |  | Yes | MR1097 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-26 12:19 | 1.1 | 2023-09-26 11:27 | 2023-09-26 11:28 | 1.2 | 196 | 196 |  | Hold | Released Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/19 | 25 | REFER ADD #1 PEN HOLDER P1 | CARRIED OUT REPLACEMENT OF P1 SIDE PENCIL HOLDER AS PER STANDARD INDUSTRIAL PRACTICES. ADD NO. 2 CLOSED. | HMV23/000059/0923/19 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1097 | 2023-09-26 11:17 | Yes | MR1097 |  | Yes | MR1097 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 0.75 | 2023-09-27 10:30 | 2023-09-28 13:23 | 0.75 | 197 | 197 |  | Hold | Released Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/20 | 11 | ADD NO. 2 FOLLOWING PLACARDS ON ENGINE #1 RH FAN COWL DEFERRED. 1. RED LINE 2. NO MAN 3. HAZARD AREA. | CARRIED OUT INSTALLATION OF RED LINE2, NO MAN AND HAZARD AREA PLACARDS ON ENGINE #1 RH FAN COWL AS PER AMM 11-00-00-400-002-A, REV 72, DATED- 01 AUG 2023.FOUND SATISFACTORY. | HMV23/000059/0923/20 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 178 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1097 | 2023-09-26 11:19 | Yes | MR1085 | B1 | Yes | MR1085 | B1 | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 2 | 2023-09-26 11:48 | 2023-09-28 12:58 | 4 | 198 | 198 |  | Hold | Released Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000059/0923/21 | 30 | TO FACILITATE LH FWD NOSE FUSELAGE DENT ASSESSMENT, WHC (2DG1), PHC (6DA1 AND 6DA3) TO BE REMOVED. | WHC (2DG1) REMOVED AS PER AMM 30-42-34-000-001-A REV 72, DT 01/08/2023. PHC (6DA1 AND 6DA3) REMOVED AS PER AMM 30-31-34-000-002-A REV 72, DT 01/08/2023. SAME WHC (2DG1) INSTALLED AS PER AMM 30-42-34-400-001-A REV 72, DT 01/08/2023. SAME PHC (6DA1 AND 6DA3) INSTALLED AS PER AMM 30-31-34-400-002-A REV 72, DT 01/08/2023. POST INSTALLATION TESTS CARRIED OUT. FOUND SATISFACTORY. | HMV23/000059/0923/21 | Close | Closed | AWR23/003125/0923 | 199 | LINE 1A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1090 | 2023-09-27 10:52 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-09-19 10:40 | 2023-09-28 12:09 | 6 | 2023-09-27 10:56 | 2023-09-28 12:28 | 8 | 201 | 201 |  | Hold | Released Estimates |  |  | 100 | [6 empty] | Hours