## Sheet1
DeleteFlag | Type | Log Item # | ATA # | Description | Corrective Action | Discrepancy # | Action | Status | Source Task/Discrep. # | Source Tracking # | Work Center # | Sign Off Status | Contract Classification | Category | Exe. Phase | Exec. Category | Part Required? | Corrosion Related? | Major Item? | Repeat? | Part # | Serial # | Position Code | Part Description | Radio Communication | Reported By | Reported Date | Mech Req? | Mech Sign Off | Mech Skill # | Insp Req? | Insp Sign Off | Insp Skill # | RII Req? | RII Sign Off | RII Skill # | Addl. Sign Off | Add New Sign Off Comments | Previous Sign Off Comments | Planned Start Date | Planned End Date | Est. Man Hrs. | Actual Start Date | Actual End Date | Actual Man Hrs. | Seq # | Tracking # | Source Tracking # | Hold Status | Estimation Status | File Name | Skill # | Zone # | Work Area # | Deferral FH | Deferral FC | Deferral Parameter | Deferral Value | Deferral Calendar Value | Deferral Calendar | Deferral Item # | Deferral Type | Reason for Deferral | Auth. Ref. # | Message Center
No | MIREP | HMV23/000055/0923/1 | 57 | DURING ARRIVAL INSPECTION , OBSERVED DENT ON SLAT NO #2 LIP AREA AT RH SIDE WING. ASSESSMENT TO BE CARRY OUT. SLAT NO #2 P/N- D5746092000500 SA7205698 | REFER SDIRC HMV23/000055/0923/7 FOR REPAIR DETAILS AND DOCUMENT REFERENCE: SRM IDENTIFICATION 57-43-21-01-A AND SRM TASK 57-40-00-283-007 AND SRM TASK 57-40-00-300-161. REVISION NO: REV: 037 DATE- AUG 01/2023 | HMV23/000055/0923/1 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1089 | 2023-09-21 08:32 | Yes | MR1089 | B1 | Yes | MR1089 | B1 | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 2 | 2023-09-22 12:39 | 2023-09-24 09:20 | 2 | 181 | 181 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/2 | 53 | DURING INSPECTION OBSERVED LH WING SLAT#5 WEATHER SEAL ERODED.SAME TO BE REPLACED. | CARRIED OUT INSTALLATION OF LH WING SLAT #5 OUT BOARD WEATHER SEAL AS PER STANDARD PRACTICES 20-21-11-911-001-A, REV 72, DT-01 AUG 2023.SECURITY OF INSTALLATION CHECK FOUND SATISFACTORY. | HMV23/000055/0923/2 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC-INTERNAL TASK | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1085 | 2023-09-21 09:00 | Yes | MR1085 | B1 | Yes | MR1085 | B1 | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 2 | 2023-09-21 09:57 | 2023-09-23 12:17 | 2 | 182 | 182 |  | Hold | Pending Estimates |  |  | 500 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/3 | 22 | DURING ARRIVAL INSPECTION FOUND FOLLOWING WARNING MSG IN PFR: 1. AUTO FLT AP OFF FURTHER RECTIFICATION TO BE CARRIED OUT. | NO FAILURE MSG RELATED TO WARNING MSG FOUND IN PFR. CARRIED OUT OPERATIONAL TEST OF THE AFS IAW AMM TASK 22-96-00-710-001-A REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. | HMV23/000055/0923/3 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Not Required | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0060 | 2023-09-21 09:00 | No |  |  | No |  |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 10 | 2023-09-24 15:20 | 2023-09-24 15:24 | 2 | 183 | 183 |  | Hold | Pending Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/4 | 34 | DURING ARRIVAL INSPECTION FOUND FOLLOWING FAILURE MSG IN PFR: 1. 34-53-31 ADF1(2RP1) FURTHER RECTIFICATION TO BE CARRIED OUT. | T/S CARRIED OUT AS PER TSM 34-53-00-810-801-A REV 72, DT 01/08/2023. ADF RECEIVER #1 REPLACED AS PER AMM 34-53-31-000-002 AND 34-53-31-400-002 REV 72, DT 01/08/2023. POST INSTALLATION BITE TEST CARRIED OUT AS PER AMM 34-53-00-740-003-A REV 72, DT 01/08/2023. FOUND SATISFACTORY. ADF RECEIVER ON/OFF PN: 822-0299-020 ON SN: 200643 OFF SN: 224833 | HMV23/000055/0923/4 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR0060 | 2023-09-21 09:02 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 5 | 2023-09-24 12:26 | 2023-09-24 12:29 | 2.5 | 184 | 184 |  | Hold | Pending Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/5 | 38 | DURING ARRIVAL INSPECTION FOUND FOLLOWING FAILURE MSG IN PFR: 1. 38-31-41 TOILET ASSY LAV F FURTHER RECTIFICATION TO BE CARRIED OUT. | CARRIED OUT TROUBLESHOOTING IAW TSM 38-31-00-810-835-A REV 72 DATED AUG 01 2023. CARRIED OUT OPEARTIONAL TEST OF THE TOILET UNIT IAW WITH AMM 38-31-00-710-009-A REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. CARRIED OUT BITE TEST OF THE VACCUM TOILET SYSTEM IAW AMM 38-31-00-740-001-A REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. | HMV23/000055/0923/5 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Not Required | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR0060 | 2023-09-21 09:04 | No |  |  | No |  |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 5 | 2023-09-24 15:03 | 2023-09-24 15:10 | 4 | 185 | 185 |  | Hold | Pending Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/6 | 57 | DURING INSPECTION, OBSERVED RH SIDE WING SLAT NO#5 WEATHER SEAL ERODED.SAME TO BE REPLACED. | CARRIED OUT INSTALLATION OF RH WING SLAT #5 OUT BOARD WEATHER SEAL AS PER STANDARD PRACTICES 20-21-11-911-001-A, REV 72, DT-01 AUG 2023.SECURITY OF INSTALLATION CHECK FOUND SATISFACTORY. | HMV23/000055/0923/6 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1089 | 2023-09-21 09:13 | Yes | MR1089 | B1 | Yes | MR1089 | B1 | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 3 | 2023-09-21 09:57 | 2023-09-24 08:55 | 3 | 186 | 186 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/7 | 57 | DURING ARRIVAL INSPECTION , OBSERVED DENT ON SLAT NO #2 LIP AREA AT RH SIDE WING. DENT LOCATION, 3 INCH FROM T/E AND 67.5 INCH FROM OUTBD EDGE .ASSESSMENT TO BE CARRY OUT. SLAT NO #2 P/N- D5746092000500 S/N- SA7205698 | 1. REFERENCE DOCUMENT DETAILS: A) DOCUMENT REFERENCE: SRM IDENTIFICATION 57-43-21-01-A AND SRM TASK 57-40-00-283-007 AND SRM TASK 57-40-00-300-161. B) REVISION NO: REV: 037 DATE- AUG 01/2023 2. PART IDENTIFICATION: A) ITEM NO: RH SLAT #2 LEADING EDGE NOSE TOP SKIN ITEM 140. B) FIGURE NO: FIGURE 57-43-21-992-001-0 (SHEET 04/5). C) SRM REFERENCE: SRM IDENTIFICATION 57-43-21-01-A. 3) DAMAGE TYPE: DENT ON RH SLAT #2 LEADING EDGE TOP NOSE SKIN 4) DAMAGE DIMENSION AND LOCATION: A) LENGTH: 84MM B) WIDTH: 35MM C) DEPTH: 1.35MM D) LOCATION: DISTANCE FROM RIB WFX5997 FASTENER ROW CENTER =76MM, DISTANCE FROM UPPER GIRDER RIVET ROW CENTER =65MM. 5) NDT INSPECTION REFERENCE AND REPORT RESULT: NIL FINDINGS. REFER HMV23/000055/0923/19 FOR NDT INSPECTION DETAILS. 6) ADL: A. SRM REFERENCE: SRM REFERENCE: SRM TASK 57-40-00-283-007. B. WITHIN ADL: DENT DEPTH IS 1.35 MM WHICH IS LESS THAN 3 MM AND CROSS-SECTIONAL AREA OF DENT IS GREATER THAN 30 X D HENCE PERMANENT DENT FILLING REPAIR IS REQUIRED TO CARRY OUT AS PER SRM TASK 57-40-00-300-161. C. WITHIN MAINTENANCE DOCUMENT REPAIR LIMITATIONS: YES. 7) REPAIR AS PER MAINTENANCE DOCUMENT: A) SRM REFERENCE FOR REPAIR: SRM TASK 57-40-00-300-161. PERMANENT DENT FILLING REPAIR CARRIED OUT AT DENTED AREA AS PER SRM TASK 57-40-00-300-161 AS REFERRED BY SRM TASK 57-40-00-283-007. 8) CLOSE UP: A) CATEGORY OF REPAIR: THIS REPAIR TASK IS CATEGORY A PERMANENT REPAIR AS PER SRM TASK 57-40-00-283-007 FIGURE 004/57-40-00-283-007(SHEET 1) AND SRM TASK 57-40-00-300-161 FIGURE 001/57-40-00-300-161 (SHEET 1). | HMV23/000055/0923/7 | Close | Closed | HMV23/000055/0923/1 | 181 | LINE 2A | Signed Off | DISC- MPD | SDIRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1089 | 2023-09-21 10:01 | Yes | MR0639 |  | Yes | MR0639 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 4 | 2023-09-21 16:58 | 2023-09-23 20:39 | 7 | 187 | 187 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/8 | 53 | DURING ARRIVAL INSPECTION, OBSERVED SMALL DENTS ON SLAT NO #1 TOP SKIN AT RH SIDE WING. LOCATION OF DENT 3.5 INCH FROM T/E AND 37 INCH FROM INBD EDGE OF SLAT. SLAT NO#1 P/N- D5746091000300 S/N- SA7205917 | REFER SDIRC HMV23/000055/0923/9 FOR REPAIR DETAILS AND DOCUMENT REFERENCE: SRM IDENTIFICATION 57-42-21-01-A AND SRM TASK 57-40-00-283-007 AND SRM TASK 57-40-00-300-161, REVISION NO: REV: 037 DATE- AUG 01/2023. | HMV23/000055/0923/8 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1089 | 2023-09-21 10:12 | Yes | MR1089 | B1 | Yes | MR1089 | B1 | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 3 | 2023-09-24 10:26 | 2023-09-24 10:32 | 3 | 188 | 188 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/9 | 57 | DURING ARRIVAL INSPECTION, OBSERVED SMALL DENTS ON SLAT NO #1 TOP SKIN AT RH SIDE WING. LOCATION OF DENT 3.5 INCH FROM T/E AND 37 INCH FROM INBD EDGE OF SLAT. SLAT NO#1 P/N- D5746091000300 S/N- SA7205917 | 1. REFERENCE DOCUMENT DETAILS: A) DOCUMENT REFERENCE: SRM IDENTIFICATION 57-42-21-01-A AND SRM TASK 57-40-00-283-007 AND SRM TASK 57-40-00-300-161. B) REVISION NO: REV: 037 DATE- AUG 01/2023. 2. PART IDENTIFICATION: A) ITEM NO: RH SLAT #1 LEADING EDGE NOSE TOP SKIN ITEM 145. B) FIGURE NO: FIGURE 57-42-21-992-001-0 (SHEET 04/5). C) SRM REFERENCE: SRM IDENTIFICATION 57-42-21-01-A. 3) DAMAGE TYPE: DENT ON RH SLAT #1 LEADING EDGE TOP NOSE SKIN 4) DAMAGE DIMENSION AND LOCATION: A) LENGTH: 28MM B) WIDTH: 25MM C) DEPTH: 0.30MM D) LOCATION: DISTANCE FROM RIB TRACK 2 RIVET ROW CENTER =109MM, DISTANCE FROM UPEER GIRDER RIVET ROW CENTER =25MM. 5) NDT INSPECTION REFERENCE AND REPORT RESULT: NIL FINDINGS. REFER HMV23/000055/0923/20 FOR NDT INSPECTION DETAILS. 6) ADL: A. SRM REFERENCE: SRM REFERENCE: SRM TASK 57-40-00-283-007. B. WITHIN ADL: DENT DEPTH IS 0.30 MM WHICH IS LESS THAN 3 MM AND CROSS-SECTIONAL AREA OF DENT IS GREATER THAN 30 X D HENCE PERMANENT DENT FILLING REPAIR IS REQUIRED TO CARRY OUT AS PER SRM TASK 57-40-00-300-161. C. WITHIN MAINTENANCE DOCUMENT REPAIR LIMITATIONS: YES. 7) REPAIR AS PER MAINTENANCE DOCUMENT: A) SRM REFERENCE FOR REPAIR: SRM TASK 57-40-00-300-161. PERMANENT DENT FILLING REPAIR CARRIED OUT AT DENTED AREA AS PER SRM TASK 57-40-00-300-161 AS REFERRED BY SRM TASK 57-40-00-283-007. 8) CLOSE UP: A) CATEGORY OF REPAIR: THIS REPAIR TASK IS CATEGORY A PERMANENT REPAIR AS PER SRM TASK 57-40-00-283-007 FIGURE 004/57-40-00-283-007(SHEET 1) AND SRM TASK 57-40-00-300-161 FIGURE 001/57-40-00-300-161 (SHEET 1). | HMV23/000055/0923/9 | Close | Closed | HMV23/000055/0923/8 | 188 | LINE 2A | Signed Off | AWR | SDIRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1089 | 2023-09-21 10:14 | Yes | MR0639 |  | Yes | MR0639 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 4 | 2023-09-21 17:05 | 2023-09-23 20:40 | 7 | 189 | 189 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/10 | 33 | DURING WEEKLY INSPECTION OBSERVED FIN: 11WL EPSU BATTERY INOP. | 1. TROUBLESHOOTING CARRIED OUT IAW TSM TASK 33-51-00-810-855-AREV 72 DTD 01 AUG 2023 FOUND EPSU BATTERY QTY#01 FIN:11WL FAULTY. 2. CARRIED OUT REMOVAL OF EPSU BATTERY FIN: 11WL IAW AMM 33-51-38-000-002-A REV 72 DTD 01 AUG 2023. OFF PN: 3214-31 OFF SN: 877186 3. CARRIED OUT INSTALLATION OF NEW EPSU BATTERY FIN: 11WL IAW AMM 33-51-38-400-002-A REV 72 DTD 01 AUG 2023. ON PN: 3214-31 ON SN: 899262 4. POST INSTALLATION CARRIED OUT OPERATIONAL CHECK OF THE EPSU BY BITE CHECK IAW AMM 33-51-00-710-001-A REV 72 DTD 01 AUG 2023. FOUND SATISFACTORY. | HMV23/000055/0923/10 | Close | Closed | AWR23/003086/0923 | 212 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0038 | 2023-09-21 10:49 | Yes | MR0067 |  | Yes | MR0067 |  | No | [5 empty] | 2023-09-21 10:49 | 2023-09-21 11:49 | 5 | 2023-09-24 09:55 | 2023-09-24 13:44 | 5 | 190 | 190 |  | Hold | Pending Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/11 | 53 | DURING INSPECTION FOUND FOLLOWING FORWARD CARGO FLOOR PANEL DAMAGED , TO BE FABRICATED/REPLACED 131 AF P/N D5367520400000 131EF P/N D5367521000000 131FF P/N D5367400800000 131BF P/N D5367401200000 131CF P/N D5367401100000 131GF P/N D5367400700000 | CARRIED OUT REMOVAL OF FWD CARGO FLOOR PANELS AS PER AMM TASK 53-22-14-000-001-A REV 72 DATED 01 AUG 2023 CARRIED OUT INSTALLATION OF FWD CARGO FLOOR PANELS AS PER AMM TASK 53-22-14-400-001-A REV 72 DATED 01 AUG 2023 . REFER FOLLOWING CWO FOR FABRICATION 131 AF P/N D5367520400000 CWO23/000386/0923 131EF P/N D5367521000000 CWO23/000387/0923 131FF P/N D5367400800000 CWO23/000395/0923 131BF P/N D5367401200000 CWO23/000397/0923 131CF P/N D5367401100000 CWO23/000405/0923 131GF P/N D5367400700000 CWO23/000406/0923 | HMV23/000055/0923/11 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-21 11:34 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-21 11:34 | 2023-09-21 12:34 | 20 | 2023-09-21 15:31 | 2023-09-24 12:42 | 15 | 192 | 192 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000055/0923/12 | 53 | DURING INSPECTION FOUND FOLLOWING AFT CARGO FLOOR PANEL DAMAGED , TO BE FABRICATED/REPLACED 151LF P/N D5367521106800 151GF P/N D5367521100400 151DF P/N D5367521100200 151EF P/N D5367402100000 151QF P/N D5367403500000 | CARRIED OUT REMOVAL OF AFT CARGO FLOOR PANELS AS PER AMM TASK 53-42-14-000-001-A REV 72 DATED 01 AUG 2023 CARRIED OUT INSTALLATION OF AFT CARGO FLOOR PANELS AS PER AMM TASK 53-42-14-400-001-A REV 72 DATED 01 AUG 2023 . REFER FOLLOWING CWO FOR FABRICATION 151LF P/N D5367521106800 CWO23/000398/0923 151GF P/N D5367521100400 CWO23/000400/0923 151DF P/N D5367521100200 CWO23/000401/0923 151EF P/N D5367402100000 CWO23/000402/0923 151QF P/N D5367403500000 CWO23/000403/0923 | HMV23/000055/0923/12 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-21 11:35 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-21 11:35 | 2023-09-21 12:35 | 20 | 2023-09-22 08:47 | 2023-09-24 12:23 | 20 | 193 | 193 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/13 | 53 | DURING ARRIVAL INSPECTION OF FORWARD CARGO , FOUND 1) CARGO SECTION HOSE MISSING/ DAMAGED 2) FOUND HARDWARE DAMAGED/MISSING | 1) FORWARD CARGO SECTION HOSE REPLACED REFER IRC HMV23/000055/0923/11 FOR DETAILS . 2) FORWARD CARGO FLOOR BOARD HARDWARE REPLACED IRC HMV23/000055/0923/11 FOR DETAILS | HMV23/000055/0923/13 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-21 12:13 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 5 | 2023-09-22 07:38 | 2023-09-24 13:10 | 5 | 194 | 194 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000055/0923/14 | 53 | DURING ARRIVAL INSPECTION OF AFT CARGO , FOUND 1) CARGO SECTION HOSE MISSING/ DAMAGED 2) FOUND HARDWARE DAMAGED/MISSING | 1) AFT CARGO SECTION HOSE AND AFT CARGO FLOOR BOARD HARDWARE REPLACED REFER IRC HMV23/000055/0923/12 FOR DETAILS . 2) AFT CARGO SIDEWALL HARDWARE INSTALLED AS PER TASK 25-55-11-400-003-A REV 72 DATED 01 AUG 2023 . | HMV23/000055/0923/14 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-21 12:14 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 5 | 2023-09-22 07:38 | 2023-09-24 13:08 | 5 | 195 | 195 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000055/0923/15 | 53 | DURING INSPECTION FOUND PISTON TYPE DRAIN VALVES FOUND DAMAGED/ DEFECTIVE | CARRIED OUT REPLACEMENT OF THE DRAIN VALVES AS AMM TASK 53-49-21-000-001-A/ TASK 53-49-21-400-001-A , REV 72 , DATED 01 AUG 2023 VALVE P/N ABS0341-2-01 | HMV23/000055/0923/15 | Close | Closed | 531900-03-1 | 123 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-21 13:00 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-22 15:39 | 4 | 2023-09-22 10:14 | 2023-09-22 15:06 | 3 | 197 | 197 |  | Hold | Pending Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/16 | 23 | DURING ARRIVAL INSPECTION OBSERVED MECHANICAL CALL HORN INOP | MECHANIC HORN REPLACED AS PER AMM 23-42-21-000-001-A AND 23-42-21-400-001-A REV 72, DT 01/08/2023. POST INSTALLATION TEST CARRIED OUT. FOUND SATISFACTORY. HORN ON/OFF PN: D0003004300000 ON SN: FAE0039886 OFF SN: FAE0035827 | HMV23/000055/0923/16 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Signed Off | AWR |  | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0038 | 2023-09-21 13:33 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 4 | 2023-09-23 15:44 | 2023-09-24 12:43 | 4 | 198 | 198 |  | Hold | Pending Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/17 | 23 | DURING ARRIVAL INSPECTION FOUND STATIC DISCHARGERS DAMAGED AT LOCATION LH WING TIP TRAILING EDGE TYPE B DISCHARGER QTY#1, RH HORZ STAB TYPE A DISCHARGER QTY#1 TYPE B DISCHARGER QTY#1, LH HORZ STAB TYPE A DISCHARGER QTY#1 TYPE B DISCHARGER QTY#3, VERT STAB TYPE A DISCHARGER QTY#1, RUDDER TYPE B DISCHARGER QTY#1. | CARRIED OUT REPLACEMENT STATIC DISCHARGERS WITH SERVICEABLE DISCHARGERS AT LOCATION RH WING, LH WING. RH HORZ STAB, LH HORZ STAB IAW AMM TASK 23-61-41-000-001-A/ AMM TASK 23-61-41-400-001-A REV 72 DTD 01 AUG/2023. | HMV23/000055/0923/17 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Not Required | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-21 14:56 | No |  |  | No |  |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 7 | 2023-09-22 07:43 | 2023-09-24 13:48 | 7 | 200 | 200 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000055/0923/18 | 21 | DURING OPPURTUNITY INSPECTION FOUND LH PLENUM BELLOW FOUND DAMAGED P/N D2157160120000 | LH PLENUM BELLOW REPLACED AS PER AMM 21-52-22-000-001 / AMM 21-52-22-000-001 REV 72 DATED 01 AUG 2023 , REFER MPD 215222-01-1 FOR REMOVAL/INSTALLATION DETAILS . BELLOW P/N D2157160120000 | HMV23/000055/0923/18 | Close | Closed | 215222-01-1 (LH) | 16 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-21 15:35 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-21 15:35 | 2023-09-21 16:35 | 2.5 | 2023-09-22 08:22 | 2023-09-23 09:33 | 4 | 201 | 201 |  | Hold | Pending Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/19 | 57 | 1.CARRY OUT HFEC INSPECTION AS PER NTM 51-10-08 ON DENT AND SURROUNDING AREA OF DENT ON RH WING SLAT#2 NOSE TOP SKIN TO ENSURE CRACK FREE CONDITION EXISTS AS REFERRED BY SRM TASK 57-40-00-283-007 REV:37 DTD:AUG 01/2023. DAMAGE DIMENSION AND LOCATION ARE DENT ON NOSE TOP SKIN OF SLAT #2 . DAMAGE DIMENSION A) LENGTH: 84MM B) WIDTH: 35MM C) DEPTH: 1.35MM D) LOCATION: DISTANCE FROM RIB WFX5997 FASTENER ROW CENTER =76MM, DISTANCE FROM UPPER GIRDER RIVET ROW CENTER =65MM | EDDY CURRENT INSPECTION CARRIED OUT ON RH WING SLAT#2. NO CRACK INDICATION OBSERVED DURING THE INSPECTION. NIL FINDINGS.FOR DETAILS REFER NDT REPORT NO: GAT/NDT/13855 | HMV23/000055/0923/19 | Close | Closed | HMV23/000055/0923/7 | 187 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR0639 | 2023-09-21 16:53 | Yes | MR0396 |  | Yes | MR0396 |  | No | [5 empty] | 2023-09-21 16:53 | 2023-09-21 17:53 | 1 | 2023-09-22 12:50 | 2023-09-23 20:30 | 1 | 202 | 202 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/20 | 57 | 1.CARRY OUT HFEC INSPECTION AS PER NTM 51-10-08 ON DENT AND SURROUNDING AREA OF DENT ON RH WING SLAT#1 NOSE TOP SKIN TO ENSURE CRACK FREE CONDITION EXISTS AS REFERRED BY SRM TASK 57-40-00-283-007 REV:37 DTD:AUG 01/2023. DAMAGE DIMENSION AND LOCATION ARE DENT ON NOSE TOP SKIN OF SLAT #1 . DAMAGE DIMENSION A) LENGTH: 28MM B) WIDTH: 25MM C) DEPTH: 0.30MM D) LOCATION: DISTANCE FROM RIB TRACK 2 RIVET ROW CENTER =109MM, DISTANCE FROM UPEER GIRDER RIVET ROW CENTER =25MM | EDDY CURRENT INSPECTION CARRIED OUT ON RH WING SLAT#1. NO CRACK INDICATION OBSERVED DURING THE INSPECTION. NIL FINDINGS. FOR DETAILS REFER NDT REPORT NO: GAT/NDT/13854 | HMV23/000055/0923/20 | Close | Closed | HMV23/000055/0923/9 | 189 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR0639 | 2023-09-21 17:08 | Yes | MR0396 |  | Yes | MR0396 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 1 | 2023-09-22 12:58 | 2023-09-23 20:35 | 1 | 203 | 203 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/21 | 33 | DURING ARRIVAL CHECK FOUND SERVICE LIGHT LAMP INOP AT FOLLOWING LOCATION 1. 80VU RH AVIONICS COMPARTMENT FIN: 9LS QTY#1, 90VU FWD AVIONICS COMPARMENT FIN: 6LS QTY#1. 2. THS COMPARMENT FIN: 5LJ QTY#1. | 1. CARRIED OUT REPLACEMENT OF SERVICE LIGHT LAMP AT LOCATION 80VU RH AVIONICS COMPARTMEN FIN: 9LS QTY#1, 90VU FWD AVIONICS COMPARMENT FIN: 6LS QTY#1 IAW AMM: 33-35-11-000-002-A/AMM 33-35-11-400-002-A REV 72 DATED AUG 01 2023. POST INSTALLATION OPERATIONAL TEST OF AVIONICS COMPARTMENT LIGHTING CARRIED OUT IAW AMM: 33-35-00-720-001 REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. 2. CARRIED OUT REPLACEMENT OF THE SERVICE LAMP FIN: 5LJ QTY#1 IN THS COMPARTMENT IAW AMM 33-31-11-000-004-A/AMM 33-31-11-400-004-A REV 72 DATED AUG 01 2023. POST INSTALLATION OPERATIONAL TEST OF THE SERVICE AREA LIGHT CARRIED OUT IAW AMM: 33-31-00- 710-001 REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. | HMV23/000055/0923/21 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 180 | LINE 2A | Not Required | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-22 07:45 | No |  |  | No |  |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 3 | 2023-09-22 07:50 | 2023-09-24 13:50 | 3 | 204 | 204 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000055/0923/22 | 53 | DURING OPP0RTUNITY INSPECTION FOUND BELLY PANEL HARDWARE DAMAGED/MISSING | BELLY PANEL HARDWARE REPLACED AS PER AMM 20-21-00 REV 72 DATED 01 AUG 2023 | HMV23/000055/0923/22 | Close | Closed | 215222-01-1 (LH) | 16 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1142 | 2023-09-22 08:25 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-22 08:25 | 2023-09-22 09:25 | 6 | 2023-09-23 06:18 | 2023-09-23 11:18 | 4 | 205 | 205 |  | Hold | Pending Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/23 | 20 | DURING WEAR LIMIT BONDING LEADS INSPECTION CHECK FOUND BONDING LEADS DAMAGED AT LOCATION TOILET SERVICE PANEL QTY#2, WATER SERVICE PANEL QTY#2, RH MLG DOOR QTY#1, LH MLG DOOR QTY#2, 108VU QTY#1, FWD CARGO DOOR QTY#1, AFT CARGO DOOR QTY#1, FWD LH PASSENGER DOOR QTY#1, RH WING FLAP TRACK FAIRING NO.2 QTY#1, RH WING FLAP TRACK FAIRING NO.3 QTY#1, LH WING FLAP TRACK FAIRING NO.1 QTY#2, LH WING FLAP TRACK FAIRING NO.3 QTY#2, LH ELEVATOR PANEL 334BB QTY#1, LH ELEVATOR PANEL 334HB QTY#1, RH ELEVATOR PANEL 344DB QTY#1, RH ELEVATOR PANEL 344BB QTY#1. | CARRIED OUT REPLACEMENT OF DAMAGED BONDING LEADS WITH SERVICEABLE BONDING LEADS AT LOCATION TOILET SERVICE PANEL QTY#2 (0.7 MILLIOHM, 0.6 MILLIOHM), WATER SERVICE PANEL QTY#2 (0.6 MILLIOHM, 0.5 MILLIOHM), RH MLG DOOR QTY# (0.5 MILLIOHM), LH MLG DOOR QTY#2 (0.5 MILLIOHM, 0.7 MILLIOHM), 108VU QTY#1(0.7 MILLIOHM), FWD CARGO DOOR QTY#1(0.5 MILLIOHM), AFT CARGO DOOR QTY#1 (0.8 MILLIOHM), FWD LH PASSENGER DOOR QTY#1 (0.7 MILLIOHM), RH WING FLAP TRACK FAIRING NO.2 QTY#1 (0.5 MILLIOHM), RH WING FLAP TRACK FAIRING NO.3 QTY#1 (0.7 MILLIOHM), LH WING FLAP TRACK FAIRING NO.1 QTY#2 (0.5 MILLIOHM, 0.7 MILLIOHM), LH WING FLAP TRACK FAIRING NO.3 QTY#2 (0.6 MILLIOHM, 0.5 MILLIOHM), LH ELEVATOR PANEL 334BB QTY#1 (0.7 MILLIOHM), LH ELEVATOR PANEL 334HB QTY#1 (0.5 MILLIOHM), RH ELEVATOR PANEL 344DB QTY#1 (0.6 MILLIOHM), RH ELEVATOR PANEL 344BB QTY#1 (0.5 MILLIOHM) IAW AMM TASK 20-28-00-912-802-A REV 72 DATED AUG 01 2023. POST INSTALLATION OF NEW BONDING LEADS BONDING TEST CARRIED OUT IAW AMM 20-28-00-869-002 REV 72 DATED AUG 01 2023. FOUND SATISFACTORY. | HMV23/000055/0923/23 | Close | Closed | WEAR LIMITS- BONDING LEADS | 135 | LINE 2A | Not Required | DISC-ADD-SB/EO/MOD/SI/SL | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-22 08:35 | No |  |  | No |  |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 24 | 2023-09-22 08:41 | 2023-09-24 13:53 | 24 | 206 | 206 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000055/0923/24 | 38 | DURING INSPECTION FOUND COMPRESSOR INLET FILTER BLOCKED , TO BE REPLACED P/N 7006-15 | COMPRESSOR INLET FILTER REPLACED REFER MPD 384241-01-1 FOR REPLACEMENT DETAILS P/N 7006-15 | HMV23/000055/0923/24 | Close | Closed | 384241-01-1 | 106 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1142 | 2023-09-22 10:03 | Yes | MR1142 |  | Yes | MR1142 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-22 11:03 | 2 | 2023-09-22 10:40 | 2023-09-22 12:59 | 2.5 | 208 | 208 |  | Hold | Pending Estimates |  |  | 100 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/25 | 25 | DURING INSPECTION OF PAX SEATS FOLLOWING FINDINGS OBSERVED:- 1. BAGGAGE BAR HARDWARES FOUND MISSING AT MULTIPLE LOCATIONS. 2. SEAT BELTS QTY 17 FOUND FRAYED AND WORN OUT. 3. ARM CAP QTY 8 FOUND DAMAGED. 4. SEAT FLANK FAIRINGS AND SPREADER FAIRING FOUND DAMAGED AT MULTIPLE LOCATIONS. | 1. MISSING BAGGAGE BAR HARDWARES REPLACED AS PER STANDARD PRACTICES AMM TASK 20-21-11-911-001-A, REV 72, DTD: 01-AUG-2023. 2. SEAT BELTS QTY 17 REPLACED AS PER AMM 25-21-42-400-002-A, REV 72, DTD: 01-AUG-2023. 3. SEAT ARM CAP QTY 8 REPLACED WITH NEW ONE AS PER STANDARD INDUSTRIAL PRACTICES. 4. FLANK FAIRINGS QTY 14 AND SPREADER FAIRINGS QTY 1 REPLACED AS PER STANDARD PRACTICES AMM TASK 20-21-11-911-001-A, REV 72, DTD: 01-AUG-2023. | HMV23/000055/0923/25 | Close | Closed | 252100-01-1 | 24 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1097 | 2023-09-22 14:13 | Yes | MR1097 |  | Yes | MR1097 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 8 | 2023-09-23 09:29 | 2023-09-24 15:45 | 8 | 209 | 209 |  | Hold | Pending Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000055/0923/26 | 26 | WHILE CARRYING OUT MPD 262300-02-1, CARGO COMPARTMENT FIRE EXTINGUISHING CHECK FIRING CIRCUIT CONTINUITY FOUND CONNECTOR 4015WX-C DAMAGED. | CARGO FIRE EXTINGUISHING BOTTLE CONNECTOR 4015WX-C REPLACED AS PER ESPM 20-44-19-01 REV 46, DT 01/08/2023. FOR POST INSTALLATION TEST REFER MPD TASK CARD 262300-02-1. FOUND SATISFACTORY. CONNECTOR ON/OFF PN: PC06E-8-2SSR ON CONNECTOR BN: 0000111311 | HMV23/000055/0923/26 | Close | Closed | 262300-02-1 | 40 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0067 | 2023-09-22 14:18 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-09-11 15:07 | 2023-09-23 12:12 | 5 | 2023-09-24 09:54 | 2023-09-24 13:39 | 6 | 210 | 210 |  | Hold | Pending Estimates |  |  | 100 | [6 empty] | Hours