## Sheet1
DeleteFlag | ATA # | Task # | Seq # | Description | Add New Execution Comments | Previous Execution Comments | Status | Source Task/Discrep. # | Source Tracking # | Work Center # | Sign Off Status | Task Type | Task Category | Job Type | Repair Class. | Exe. Phase | Exec. Category | Part # | Serial # | Position Code | Part Description | Repair Agency | Mech Req? | Mech Sign Off | Insp Req? | Insp Sign Off | RII Req? | RII Sign Off | Addl. Sign Off | Add New Sign Off Comments | Previous Sign Off Comments | Planned Start Date | Planned End Date | Est. Man Hrs. | Actual Start Date | Actual End Date | Actual Man Hrs. | Tracking # | Maint. Manual Ref. # | Long Description | Hold Status | Estimation Status | File Name | Skill # | Zone # | Work Area # | WBS Code | Parent Task # | Root Task # | Workscoping Comments | Message Center
No | 5 | 1C+EOS | 1 | CARRY OUT 1C+ EO's CHECK ON AIRCRAFT |  |  | Closed |  |  | LINE 2A | Not Required | Others | MAINT | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-13 12:08 | 341.2 | 2023-09-22 08:31 | 2023-09-24 15:51 | 50 | 1 |  | CARRY OUT 1C+ EO's CHECK ON AIRCRAFT | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 24 | 200002-01-1 | 2 | HIRF/LIGHTNING PROTECTION-THS T/E GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE FOLLOWING HARNESSES: - 405VB, 406VB, 407VB, 408VB, 409VB, LH SI |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:02 | 2.07 | 2023-09-23 12:16 | 2023-09-23 13:16 | 4 | 2 |  | HIRF/LIGHTNING PROTECTION-THS T/E GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE FOLLOWING HARNESSES: - 405VB, 406VB, 407VB, 408VB, 409VB, LH SIDE - 400VB, 401VB, 402VB, 403VB, 404VB, RH SIDE | Hold | Pending Estimates |  | B2 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 2001-16-09 | 3 | FLIGHT CONTROLS - ELEVATOR BACKLASH - INSPECTION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | AD | MAINT | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:38 | 2.76 | 2023-09-23 12:58 | 2023-09-23 13:58 | 4 | 3 |  | FLIGHT CONTROLS - ELEVATOR BACKLASH - INSPECTION | Hold | Pending Estimates |  | B1 |  |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 200121-01-1 | 4 | FORWARD AVIONIC COMPARTMENT CLEANING OF EWIS INSTALLED IN THE FORWARD AVIONIC COMPARTMENT (ONLY IF CONTAMINATED)(EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | RST | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:53 | 1.72 | 2023-09-23 09:08 | 2023-09-23 10:08 | 5 | 4 |  | FORWARD AVIONIC COMPARTMENT CLEANING OF EWIS INSTALLED IN THE FORWARD AVIONIC COMPARTMENT (ONLY IF CONTAMINATED)(EWIS) | Hold | Pending Estimates |  | B2 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 200413-05-1 (LH) | 5 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:14 | 2.56 | 2023-09-23 12:19 | 2023-09-23 13:19 | 3.5 | 5 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 200413-05-1 (RH) | 6 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:14 | 2.56 | 2023-09-22 13:55 | 2023-09-22 14:55 | 3.5 | 6 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 200415-02-1 (LH) | 7 | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:44 | 1.4 | 2023-09-23 12:18 | 2023-09-23 13:18 | 3 | 7 |  | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 200415-02-1 (RH) | 8 | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:44 | 1.4 | 2023-09-22 13:54 | 2023-09-22 14:54 | 3 | 8 |  | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 200471-02-1 (LH) | 9 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:45 | 1.44 | 2023-09-23 12:17 | 2023-09-23 13:17 | 3 | 9 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 200471-02-1 (RH) | 10 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:45 | 1.44 | 2023-09-22 13:53 | 2023-09-22 14:53 | 3 | 10 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 212600-03-1 | 11 | AVIONICS EQUIPMENT VENTILATION OPERATIONAL CHECK OF SMOKE CONFIGURATION CONTROL CIRCUIT |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:13 | 0.23 | 2023-09-24 09:42 | 2023-09-24 10:42 | 2 | 11 |  | AVIONICS EQUIPMENT VENTILATION OPERATIONAL CHECK OF SMOKE CONFIGURATION CONTROL CIRCUIT | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 12 | 212600-09-1 | 12 | AVIONICS EQUIPMENT VENTILATION CLEAN GRID OF RELAY BOX VU PANELS NOTE: DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | RST | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:26 | 0.69 | 2023-09-22 11:43 | 2023-09-22 12:43 | 2 | 12 |  | AVIONICS EQUIPMENT VENTILATION CLEAN GRID OF RELAY BOX VU PANELS NOTE: DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT OR MORE FREQUENT INITIAL INTERVAL MAY BE USED. | Hold | Pending Estimates |  | B2 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 213100-01-1 | 13 | PRESSURE CONTROL AND MONITORING OPERATIONAL CHECK OF SYSTEM VIA MCDU |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-21 13:48 | 2023-09-21 14:48 | 1.2 | 13 |  | PRESSURE CONTROL AND MONITORING OPERATIONAL CHECK OF SYSTEM VIA MCDU | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 213100-02-1 | 14 | PRESSURE CONTROL AND MONITORING OPERATIONAL CHECK OF MANUAL MODE SELECTION AND MANUAL MODE PRESSURE CONTROL AND FUNCTIONAL CHECK OF MANUAL MODE CABIN |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | mr0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.46 | 2023-09-21 13:56 | 2023-09-21 14:56 | 1.2 | 14 |  | PRESSURE CONTROL AND MONITORING OPERATIONAL CHECK OF MANUAL MODE SELECTION AND MANUAL MODE PRESSURE CONTROL AND FUNCTIONAL CHECK OF MANUAL MODE CABIN ALTITUDE INDICATION AND OUTFLOW VALVE POSITION INDICATION | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 215000-03-2 | 15 | PACK RAM AIR INLET DETAILED INSPECTION OF ACTUATOR MECHANISM AND INLET FLAP FOR EXCESSIVE PLAY AND CHECK GAP BETWEEN INLET NOSE AND DIFFUSER RAMP |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:08 | 2.3 | 2023-09-22 09:10 | 2023-09-22 10:10 | 3 | 15 |  | PACK RAM AIR INLET DETAILED INSPECTION OF ACTUATOR MECHANISM AND INLET FLAP FOR EXCESSIVE PLAY AND CHECK GAP BETWEEN INLET NOSE AND DIFFUSER RAMP | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 215222-01-1 (LH) | 16 | PLENUM CHAMBER DETAILED INSPECTION OF INTERIOR AND EXTERIOR OF PLENUM CHAMBER (10HM5 AND 11HM5) FOR SIGNS OF DELAMINATION NOTE: PLANNING: - IT IS RE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:01 | 2.04 | 2023-09-23 10:24 | 2023-09-23 11:24 | 5 | 16 |  | PLENUM CHAMBER DETAILED INSPECTION OF INTERIOR AND EXTERIOR OF PLENUM CHAMBER (10HM5 AND 11HM5) FOR SIGNS OF DELAMINATION NOTE: PLANNING: - IT IS RECOMMENDED TO PERFORMED THIS TASK AT THE SAME TIME AS TASK 215200-01-1. INTERVAL: - DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT OR MORE FREQUENT INITIAL INTERVAL MAY BE USED. | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 215222-01-1 (RH) | 17 | PLENUM CHAMBER DETAILED INSPECTION OF INTERIOR AND EXTERIOR OF PLENUM CHAMBER (10HM5 AND 11HM5) FOR SIGNS OF DELAMINATION NOTE: PLANNING: - IT IS RE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:01 | 2.04 | 2023-09-23 11:49 | 2023-09-23 12:49 | 6 | 17 |  | PLENUM CHAMBER DETAILED INSPECTION OF INTERIOR AND EXTERIOR OF PLENUM CHAMBER (10HM5 AND 11HM5) FOR SIGNS OF DELAMINATION NOTE: PLANNING: - IT IS RECOMMENDED TO PERFORMED THIS TASK AT THE SAME TIME AS TASK 215200-01-1. INTERVAL: - DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT OR MORE FREQUENT INITIAL INTERVAL MAY BE USED. | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 216242-01-1 (LH) | 18 | AIR COOLING AND TEMPERATURE CONTROL DETAILED INSPECTION OF TRIM AIR CHECK VALVES FLAPPERS FOR CONDITION AND OPERATION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.4 | 2023-09-21 09:55 | 2023-09-23 11:01 | 6 | 18 |  | AIR COOLING AND TEMPERATURE CONTROL DETAILED INSPECTION OF TRIM AIR CHECK VALVES FLAPPERS FOR CONDITION AND OPERATION | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 21 | 216242-01-1 (RH) | 19 | AIR COOLING AND TEMPERATURE CONTROL DETAILED INSPECTION OF TRIM AIR CHECK VALVES FLAPPERS FOR CONDITION AND OPERATION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.4 | 2023-09-21 09:55 | 2023-09-23 12:45 | 6 | 19 |  | AIR COOLING AND TEMPERATURE CONTROL DETAILED INSPECTION OF TRIM AIR CHECK VALVES FLAPPERS FOR CONDITION AND OPERATION | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 23 | 237100-01-1 | 20 | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF CVR AND CVR-CHANNEL RECORDING |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:32 | 0.92 | 2023-09-22 07:54 | 2023-09-22 08:54 | 1.5 | 20 |  | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF CVR AND CVR-CHANNEL RECORDING | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 23 | 237135-02-1 | 21 | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF ULB |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0067 | Yes | mr0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.39 | 2023-09-24 11:25 | 2023-09-24 12:25 | 2 | 21 |  | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF ULB | Hold | Pending Estimates |  | B2 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 242200-01-1 | 22 | AC GENERATION OPERATIONAL CHECK OF TRANSFER INHIBITION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-22 07:55 | 2023-09-22 08:55 | 1.5 | 22 |  | AC GENERATION OPERATIONAL CHECK OF TRANSFER INHIBITION | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 24 | 243400-01-1 | 23 | DC GENERATION OPERATIONAL CHECK OF "DC EMERG. CONFIG" CAUTION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | Yes | MR0032 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:17 | 0.34 | 2023-09-21 13:00 | 2023-09-21 14:00 | 1.05 | 23 |  | DC GENERATION OPERATIONAL CHECK OF "DC EMERG. CONFIG" CAUTION | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 25 | 252100-01-1 | 24 | PASSENGER COMPARTMENT SEATS DETAILED INSPECTION OF SEAT ATTACHMENTS, SEAT STRUCTURE, SEAT BELTS, BUCKLES AND BAGGAGE BAR. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0001 | Yes | MR0001 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 17:08 | 4.6 | 2023-09-24 14:51 | 2023-09-24 15:51 | 20 | 24 |  | PASSENGER COMPARTMENT SEATS DETAILED INSPECTION OF SEAT ATTACHMENTS, SEAT STRUCTURE, SEAT BELTS, BUCKLES AND BAGGAGE BAR. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 25 | 252200-01-1 | 25 | CABIN ATTENDANT SEATS DETAILED INSPECTION OF CABIN ATTENDANT SEAT ATTACHMENTS, SEAT STRUCTURE AND SEAT BELT (INCLUDING SEAT BELT ATTACHMENTS AND BUCK |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:26 | 0.69 | 2023-09-22 13:42 | 2023-09-22 14:42 | 1.5 | 25 |  | CABIN ATTENDANT SEATS DETAILED INSPECTION OF CABIN ATTENDANT SEAT ATTACHMENTS, SEAT STRUCTURE AND SEAT BELT (INCLUDING SEAT BELT ATTACHMENTS AND BUCKLES). | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 25 | 252200-03-1 | 26 | CABIN ATTENDANT SEATS OPERATIONAL CHECK OF SEAT BELTS (INCLUDING HARNESS ROLL-UP MECHANISM). |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:08 | 0.5 | 2023-09-22 13:43 | 2023-09-22 14:43 | 1.5 | 26 |  | CABIN ATTENDANT SEATS OPERATIONAL CHECK OF SEAT BELTS (INCLUDING HARNESS ROLL-UP MECHANISM). | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 25 | 254000-04-2 | 27 | LAVATORIES DETAILED INSPECTION OF LAVATORY FLOOR PAN |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:38 | 3.45 | 2023-09-22 13:44 | 2023-09-22 14:44 | 5 | 27 |  | LAVATORIES DETAILED INSPECTION OF LAVATORY FLOOR PAN | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 25 | 256535-01-1 | 28 | ELT (REAR FUSELAGE) OPERATIONAL CHECK OF ELT SYSTEM BY MANUAL ACTIVATION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-23 15:02 | 2023-09-23 16:02 | 1.5 | 28 |  | ELT (REAR FUSELAGE) OPERATIONAL CHECK OF ELT SYSTEM BY MANUAL ACTIVATION | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 25 | 256535-04-1 | 29 | ELT (REAR FUSELAGE)- GENERAL VISUAL INSPECTION OF EXTERNAL ELT ANTENNA |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | GVI | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 16:37 | 3 | 2023-09-24 11:26 | 2023-09-24 12:26 | 5 | 29 |  | ELT (REAR FUSELAGE)- GENERAL VISUAL INSPECTION OF EXTERNAL ELT ANTENNA | Hold | Pending Estimates |  | B1 |  |  | TASK | 1C+EOS | 1C+EOS
No | 25 | 256536-01-1 | 30 | BEACON - LOW FREQUENCY UNDERWATER LOCATOR OPERATIONAL CHECK OF LOW FREQUENCY UNDERWATER LOCATOR BEACON. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | OPC | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:38 | 2.5 | 2023-09-22 13:17 | 2023-09-22 14:17 | 2.5 | 30 |  | BEACON - LOW FREQUENCY UNDERWATER LOCATOR OPERATIONAL CHECK OF LOW FREQUENCY UNDERWATER LOCATOR BEACON. | Hold | Pending Estimates |  | B2 |  |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 261500-03-1 | 31 | AVIONICS COMPARTMENT SMOKE DETECTION CLEAN AVIONICS SMOKE DETECTION PICCOLO TUBES |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | RST | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0001 | Yes | mr0001 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.29 | 2023-09-22 07:46 | 2023-09-24 13:33 | 2 | 31 |  | AVIONICS COMPARTMENT SMOKE DETECTION CLEAN AVIONICS SMOKE DETECTION PICCOLO TUBES | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-02-1 (LH) | 32 | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF BOTTLE LOW PRESSURE INDICATING CIRCUIT |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:13 | 0.23 | 2023-09-24 11:26 | 2023-09-24 12:26 | 3 | 32 |  | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF BOTTLE LOW PRESSURE INDICATING CIRCUIT | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-02-1 (RH) | 33 | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF BOTTLE LOW PRESSURE INDICATING CIRCUIT |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-22 07:53 | 2023-09-22 08:53 | 1.5 | 33 |  | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF BOTTLE LOW PRESSURE INDICATING CIRCUIT | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-03-1 (LH) | 34 | ENGINE FIRE EXTINGUISHING CHECK FIRING CIRCUIT CONTINUITY |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:21 | 0.55 | 2023-09-24 12:31 | 2023-09-24 13:31 | 2 | 34 |  | ENGINE FIRE EXTINGUISHING CHECK FIRING CIRCUIT CONTINUITY | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-03-1 (RH) | 35 | ENGINE FIRE EXTINGUISHING CHECK FIRING CIRCUIT CONTINUITY |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:22 | 0.55 | 2023-09-22 07:51 | 2023-09-22 08:51 | 2 | 35 |  | ENGINE FIRE EXTINGUISHING CHECK FIRING CIRCUIT CONTINUITY | Hold | Pending Estimates |  | B2 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-05-1 (LH) | 36 | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF FIRE CONTROL PUSH BUTTON SWITCH SUB FUNCTIONS RELATED TO ENGINE SHUTDOWN AND ISOLATION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:26 | 0.75 | 2023-09-24 12:31 | 2023-09-24 13:31 | 2 | 36 |  | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF FIRE CONTROL PUSH BUTTON SWITCH SUB FUNCTIONS RELATED TO ENGINE SHUTDOWN AND ISOLATION | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-05-1 (RH) | 37 | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF FIRE CONTROL PUSH BUTTON SWITCH SUB FUNCTIONS RELATED TO ENGINE SHUTDOWN AND ISOLATION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:27 | 0.75 | 2023-09-22 07:58 | 2023-09-22 08:58 | 2.5 | 37 |  | ENGINE FIRE EXTINGUISHING OPERATIONAL CHECK OF FIRE CONTROL PUSH BUTTON SWITCH SUB FUNCTIONS RELATED TO ENGINE SHUTDOWN AND ISOLATION | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-07-1 (LH) | 38 | ENGINE FIRE EXTINGUISHING CHECK DISTRIBUTION PIPING TO DETECT LEAKAGE AND OBSTRUCTION. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:32 | 3.22 | 2023-09-22 07:50 | 2023-09-23 16:07 | 5 | 38 |  | ENGINE FIRE EXTINGUISHING CHECK DISTRIBUTION PIPING TO DETECT LEAKAGE AND OBSTRUCTION. | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262100-07-1 (RH) | 39 | ENGINE FIRE EXTINGUISHING CHECK DISTRIBUTION PIPING TO DETECT LEAKAGE AND OBSTRUCTION. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:32 | 3.22 | 2023-09-22 09:20 | 2023-09-24 09:27 | 5 | 39 |  | ENGINE FIRE EXTINGUISHING CHECK DISTRIBUTION PIPING TO DETECT LEAKAGE AND OBSTRUCTION. | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262300-02-1 | 40 | CARGO COMPARTMENT FIRE EXTINGUISHING CHECK FIRING CIRCUIT CONTINUITY |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:44 | 1.38 | 2023-09-24 12:40 | 2023-09-24 13:40 | 3 | 40 |  | CARGO COMPARTMENT FIRE EXTINGUISHING CHECK FIRING CIRCUIT CONTINUITY | Hold | Pending Estimates |  | B2 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 26 | 262541-04-1 | 41 | LAVATORY FIRE EXTINGUISHING VISUAL CHECK OF FIRE EXTINGUISHER BOTTLE PRESSURE READING |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-22 13:45 | 2023-09-22 14:45 | 0.5 | 41 |  | LAVATORY FIRE EXTINGUISHING VISUAL CHECK OF FIRE EXTINGUISHER BOTTLE PRESSURE READING | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 271400-02-2 (LH) | 42 | AILERON HYDRAULIC ACTUATION CHECK AILERON SERVO CONTROL AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:16 | 2.63 | 2023-09-23 08:52 | 2023-09-23 09:52 | 4 | 42 |  | AILERON HYDRAULIC ACTUATION CHECK AILERON SERVO CONTROL AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 271400-02-2 (RH) | 43 | AILERON HYDRAULIC ACTUATION CHECK AILERON SERVO CONTROL AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:16 | 2.63 | 2023-09-23 09:08 | 2023-09-23 10:08 | 4 | 43 |  | AILERON HYDRAULIC ACTUATION CHECK AILERON SERVO CONTROL AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 272100-12-1 | 44 | RUDDER MECHANICAL CONTROL LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | LUB | Aircraft |  | SRV/LUB | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:08 | 1 | 2023-09-23 06:40 | 2023-09-23 15:24 | 2 | 44 |  | RUDDER MECHANICAL CONTROL LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | Hold | Pending Estimates |  | B1 |  |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 272145-01-1 | 45 | RUDDER CABLE TENSION REGULATOR FUNCTIONAL CHECK OF TENSION REGULATOR (POINTER WITHIN THE LIMITS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:29 | 0.8 | 2023-09-23 12:55 | 2023-09-23 13:55 | 1.5 | 45 |  | RUDDER CABLE TENSION REGULATOR FUNCTIONAL CHECK OF TENSION REGULATOR (POINTER WITHIN THE LIMITS) | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 272400-02-1 | 46 | RUDDER HYDRAULIC ACTUATION CHECK RUDDER SERVOCONTROL AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:12 | 2.48 | 2023-09-23 07:01 | 2023-09-23 13:57 | 6 | 46 |  | RUDDER HYDRAULIC ACTUATION CHECK RUDDER SERVOCONTROL AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 274142-01-1 | 47 | THS TRIM CTL CABLE TENSION COMPENSATOR FUNCTIONAL CHECK OF POINTER ON TENSION COMPENSATOR (SCALE WITHIN LIMITS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:12 | 0.16 | 2023-09-23 12:49 | 2023-09-23 13:49 | 1.5 | 47 |  | THS TRIM CTL CABLE TENSION COMPENSATOR FUNCTIONAL CHECK OF POINTER ON TENSION COMPENSATOR (SCALE WITHIN LIMITS) | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 274451-04-1 | 48 | THS ACTUATOR DETAILED INSPECTION OF THS ACTUATOR BALL SCREW NUT BODY AND SCREW AND CLAW STOPS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.39 | 2023-09-23 12:50 | 2023-09-23 13:50 | 1.5 | 48 |  | THS ACTUATOR DETAILED INSPECTION OF THS ACTUATOR BALL SCREW NUT BODY AND SCREW AND CLAW STOPS | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 274451-05-1 | 49 | THS ACTUATOR DETAILED INSPECTION OF UPPER AND LOWER THS ACTUATOR ATTACHMENT (PRIMARY AND SECONDARY) NOTE: FOR NEO A/C ONLY: PLANNING: - ENSURE THAT |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.39 | 2023-09-23 12:50 | 2023-09-23 13:50 | 1.5 | 49 |  | THS ACTUATOR DETAILED INSPECTION OF UPPER AND LOWER THS ACTUATOR ATTACHMENT (PRIMARY AND SECONDARY) NOTE: FOR NEO A/C ONLY: PLANNING: - ENSURE THAT INSPECTIONS ACCORDING 274451-10-1 AND 274451-11-1 ARE CARRIED OUT PRIOR TO TASK 274451-05-1 (AND PRIOR TO ANY CLEANING), WHEN PLANNED AT THE SAME TIME | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 274451-06-1 | 50 | THS ACTUATOR VISUAL CHECK OF THS ACTUATOR THREADED NUT (FAIL SAFE NUT) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:12 | 0.16 | 2023-09-23 12:51 | 2023-09-23 13:51 | 0.5 | 50 |  | THS ACTUATOR VISUAL CHECK OF THS ACTUATOR THREADED NUT (FAIL SAFE NUT) | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 274451-08-1 | 51 | THS ACTUATOR CHECK INTEGRITY OF THS ACTUATOR BALL SCREW SHAFT (PRIMARY AND SECONDARY LOAD PATH) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.27 | 2023-09-22 11:19 | 2023-09-23 13:51 | 6 | 51 |  | THS ACTUATOR CHECK INTEGRITY OF THS ACTUATOR BALL SCREW SHAFT (PRIMARY AND SECONDARY LOAD PATH) | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 274451-09-1 | 52 | THS ACTUATOR DRAIN AND REFILL THS ACTUATOR GEARBOX |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | SVC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:39 | 1.19 | 2023-09-23 06:40 | 2023-09-23 13:55 | 2 | 52 |  | THS ACTUATOR DRAIN AND REFILL THS ACTUATOR GEARBOX | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 274451-14-1 | 53 | THS ACTUATOR OPERATIONAL CHECK OF THS ACTUATOR ELECTRICAL LOAD SENSING DEVICE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:28 | 0.8 | 2023-09-21 12:41 | 2023-09-21 13:41 | 2 | 53 |  | THS ACTUATOR OPERATIONAL CHECK OF THS ACTUATOR ELECTRICAL LOAD SENSING DEVICE | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 275100-01-2 | 54 | FLAPS OPERATIONAL CHECK OF WTB/POB NOTE: FLAP SURFACES MOVE AUTOMATICALLY |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | mr0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:26 | 0.69 | 2023-09-23 14:26 | 2023-09-23 15:26 | 1 | 54 |  | FLAPS OPERATIONAL CHECK OF WTB/POB NOTE: FLAP SURFACES MOVE AUTOMATICALLY | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 275100-02-1 (LH) | 55 | FLAPS - OPERATIONAL CHECK OF FLAP INTERCONNECTING STRUT AND FLAP DISCONNECT PROXIMITY SENSORS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | POST DOCK | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 1 | 2023-09-21 10:01 | 2023-09-22 10:33 | 3 | 55 |  | FLAPS OPERATIONAL CHECK OF FLAP INTERCONNECTING STRUT AND FLAP DISCONNECT PROXIMITY SENSORS | Hold | Pending Estimates |  | B1 |  |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 275100-02-1 (RH) | 56 | FLAPS - OPERATIONAL CHECK OF FLAP INTERCONNECTING STRUT AND FLAP DISCONNECT PROXIMITY SENSORS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | POST DOCK | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 1 | 2023-09-21 09:59 | 2023-09-22 10:34 | 3 | 56 |  | FLAPS - OPERATIONAL CHECK OF FLAP INTERCONNECTING STRUT AND FLAP DISCONNECT PROXIMITY SENSORS | Hold | Pending Estimates |  | B1 |  |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 275100-03-1 (LH) | 57 | FLAPS CHECK OF FLAPS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | CHK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:33 | 0.98 | 2023-09-21 13:53 | 2023-09-21 14:53 | 4 | 57 |  | FLAPS CHECK OF FLAPS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS. | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 275100-03-1 (RH) | 58 | FLAPS CHECK OF FLAPS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | CHK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:33 | 0.98 | 2023-09-23 16:05 | 2023-09-23 17:05 | 4 | 58 |  | FLAPS CHECK OF FLAPS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS. | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 275144-01-1 (LH) | 59 | FLAP INTERCONNECTING STRUT DETAILED INSPECTION OF INTERCONNECTING STRUT AND ATTACHMENTS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:27 | 0.73 | 2023-09-21 09:35 | 2023-09-23 09:54 | 3 | 59 |  | FLAP INTERCONNECTING STRUT DETAILED INSPECTION OF INTERCONNECTING STRUT AND ATTACHMENTS | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 275144-01-1 (RH) | 60 | FLAP INTERCONNECTING STRUT DETAILED INSPECTION OF INTERCONNECTING STRUT AND ATTACHMENTS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:27 | 0.73 | 2023-09-21 09:58 | 2023-09-22 10:32 | 2.5 | 60 |  | FLAP INTERCONNECTING STRUT DETAILED INSPECTION OF INTERCONNECTING STRUT AND ATTACHMENTS | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 12 | 275451-01-1 | 61 | FLAP POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | SVC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.27 | 2023-09-22 07:49 | 2023-09-22 13:04 | 3 | 61 |  | FLAP POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 276400-02-1 (LH) | 62 | SPOILER AND HYDRAULIC ACTUATION CHECK SPOILER SERVOCONTROL BEARING AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:33 | 3.26 | 2023-09-23 08:53 | 2023-09-23 09:53 | 3 | 62 |  | SPOILER AND HYDRAULIC ACTUATION CHECK SPOILER SERVOCONTROL BEARING AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 276400-02-1 (RH) | 63 | SPOILER AND HYDRAULIC ACTUATION CHECK SPOILER SERVOCONTROL BEARING AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:33 | 3.26 | 2023-09-23 09:10 | 2023-09-23 10:10 | 4.5 | 63 |  | SPOILER AND HYDRAULIC ACTUATION CHECK SPOILER SERVOCONTROL BEARING AND HINGE BEARINGS FOR EXCESSIVE PLAY AND CONDITION | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 278100-03-1 | 64 | SLATS OPERATIONAL CHECK OF WTB/POB |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | mr0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:20 | 0.46 | 2023-09-23 14:27 | 2023-09-23 15:27 | 1.1 | 64 |  | SLATS OPERATIONAL CHECK OF WTB/POB | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 278100-04-1 (LH) | 65 | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | CHK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:24 | 2.94 | 2023-09-22 10:17 | 2023-09-23 11:55 | 10 | 65 |  | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 27 | 278100-04-1 (RH) | 66 | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | CHK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:24 | 2.94 | 2023-09-22 10:18 | 2023-09-24 09:30 | 10 | 66 |  | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 12 | 278451-01-1 | 67 | SLAT POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | SVC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.27 | 2023-09-22 07:49 | 2023-09-22 13:05 | 2.5 | 67 |  | SLAT POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 281247-01-1 (LH) | 68 | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:09 | 0.5 | 2023-09-21 14:03 | 2023-09-21 15:03 | 2 | 68 |  | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 281247-01-1 (RH) | 69 | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:09 | 0.5 | 2023-09-22 08:25 | 2023-09-22 09:25 | 2 | 69 |  | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 281600-01-1 (LH) | 70 | FUEL RECIRCULATION COOLING OPERATIONAL CHECK OF PYLON CHECK VALVE TO ENSURE VALVE NOT FAILED OPEN |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-23 15:08 | 2023-09-23 16:08 | 3 | 70 |  | FUEL RECIRCULATION COOLING OPERATIONAL CHECK OF PYLON CHECK VALVE TO ENSURE VALVE NOT FAILED OPEN | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 281600-01-1 (RH) | 71 | FUEL RECIRCULATION COOLING OPERATIONAL CHECK OF PYLON CHECK VALVE TO ENSURE VALVE NOT FAILED OPEN |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-24 08:43 | 2023-09-24 09:43 | 3 | 71 |  | FUEL RECIRCULATION COOLING OPERATIONAL CHECK OF PYLON CHECK VALVE TO ENSURE VALVE NOT FAILED OPEN | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 282100-05-1 (LH) | 72 | FUEL PUMP SYSTEM VISUAL CHECK OF PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO DISCONNECT PANEL FOR LEAKS WITH BOOSTER PUMP ON AN |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-23 08:50 | 2023-09-23 09:50 | 2 | 72 |  | FUEL PUMP SYSTEM VISUAL CHECK OF PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO DISCONNECT PANEL FOR LEAKS WITH BOOSTER PUMP ON AND LP VALVE OPEN | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 282100-05-1 (RH) | 73 | FUEL PUMP SYSTEM VISUAL CHECK OF PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO DISCONNECT PANEL FOR LEAKS WITH BOOSTER PUMP ON AN |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-22 12:58 | 2023-09-22 13:58 | 2 | 73 |  | FUEL PUMP SYSTEM VISUAL CHECK OF PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO DISCONNECT PANEL FOR LEAKS WITH BOOSTER PUMP ON AND LP VALVE OPEN | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 282300-01-2 | 74 | CROSSFEED SYSTEM OPERATIONAL CHECK OF CROSSFEED VALVE USING INDIVIDUAL MOTORS AND CHECK FUEL FLOW IN "OPEN" AND FUEL SHUT OFF IN "CLOSED" POSITIONS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.27 | 2023-09-21 13:45 | 2023-09-21 14:45 | 2 | 74 |  | CROSSFEED SYSTEM OPERATIONAL CHECK OF CROSSFEED VALVE USING INDIVIDUAL MOTORS AND CHECK FUEL FLOW IN "OPEN" AND FUEL SHUT OFF IN "CLOSED" POSITIONS | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 282400-01-1 (LH) | 75 | ENGINE LOW PRESSURE SHUT OFF OPERATIONAL CHECK OF LP SHUT OFF VALVES AND THEIR CONTROLS TO ENSURE NO FLOW WHEN SELECTED CLOSED WITH BOOSTER PUMP ON |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:11 | 0.11 | 2023-09-22 06:34 | 2023-09-23 09:48 | 4 | 75 |  | ENGINE LOW PRESSURE SHUT OFF OPERATIONAL CHECK OF LP SHUT OFF VALVES AND THEIR CONTROLS TO ENSURE NO FLOW WHEN SELECTED CLOSED WITH BOOSTER PUMP ON NOTE: INTERVAL: - TASK MAY BE PERFORMED AT OPPORTUNITY OF ENGINE REMOVAL PROVIDED INTERVAL NOT EXCEEDED | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 28 | 282400-01-1 (RH) | 76 | ENGINE LOW PRESSURE SHUT OFF OPERATIONAL CHECK OF LP SHUT OFF VALVES AND THEIR CONTROLS TO ENSURE NO FLOW WHEN SELECTED CLOSED WITH BOOSTER PUMP ON |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:11 | 0.11 | 2023-09-22 06:35 | 2023-09-22 13:56 | 4 | 76 |  | ENGINE LOW PRESSURE SHUT OFF OPERATIONAL CHECK OF LP SHUT OFF VALVES AND THEIR CONTROLS TO ENSURE NO FLOW WHEN SELECTED CLOSED WITH BOOSTER PUMP ON NOTE: INTERVAL: - TASK MAY BE PERFORMED AT OPPORTUNITY OF ENGINE REMOVAL PROVIDED INTERVAL NOT EXCEEDED | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291000-06-1 | 77 | MAIN HYDRAULIC POWER FUNCTIONAL CHECK OF PTU YELLOW TO GREEN |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-23 12:58 | 2023-09-23 13:58 | 1 | 77 |  | MAIN HYDRAULIC POWER FUNCTIONAL CHECK OF PTU YELLOW TO GREEN | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291000-09-1 (LH) | 78 | MAIN HYDRAULIC POWER OPERATIONAL CHECK OF HYDRAULIC FIRE SHUT OFF VALVES AND ASSOCIATED INDICATING SYSTEM. NOTE: APPLICABLE FOR PRE 22155 IF ACTUATO |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:22 | 0.55 | 2023-09-21 14:02 | 2023-09-21 15:02 | 2 | 78 |  | MAIN HYDRAULIC POWER OPERATIONAL CHECK OF HYDRAULIC FIRE SHUT OFF VALVES AND ASSOCIATED INDICATING SYSTEM. NOTE: APPLICABLE FOR PRE 22155 IF ACTUATOR P/N E0 1100 AMENDMENT A, OR P/N E0 1100 AMENDMENT AB, OR P/N E0 1100 AMENDMENT AC, OR P/N E0 1100 AMENDMENT BC, OR P/N E0 1100 AMENDMENT C, OR P/N A06 A00 IS INSTALLED | Hold | Pending Estimates |  |  |  |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291000-09-1 (RH) | 79 | MAIN HYDRAULIC POWER OPERATIONAL CHECK OF HYDRAULIC FIRE SHUT OFF VALVES AND ASSOCIATED INDICATING SYSTEM. NOTE: APPLICABLE FOR PRE 22155 IF ACTUATO |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:22 | 0.55 | 2023-09-22 08:24 | 2023-09-22 09:24 | 1.5 | 79 |  | MAIN HYDRAULIC POWER OPERATIONAL CHECK OF HYDRAULIC FIRE SHUT OFF VALVES AND ASSOCIATED INDICATING SYSTEM. NOTE: APPLICABLE FOR PRE 22155 IF ACTUATOR P/N E0 1100 AMENDMENT A, OR P/N E0 1100 AMENDMENT AB, OR P/N E0 1100 AMENDMENT AC, OR P/N E0 1100 AMENDMENT BC, OR P/N E0 1100 AMENDMENT C, OR P/N A06 A00 IS INSTALLED | Hold | Pending Estimates |  |  |  |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291000-19-1 | 80 | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF PTU IN-FLIGHT INHIBITION LOGIC |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:55 | 1.86 | 2023-09-24 11:26 | 2023-09-24 12:26 | 4 | 80 |  | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF PTU IN-FLIGHT INHIBITION LOGIC | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291000-20-1 | 81 | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF EDP DEPESSURIZATION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:23 | 0.57 | 2023-09-22 08:21 | 2023-09-22 09:21 | 1.5 | 81 |  | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF EDP DEPESSURIZATION | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291000-21-1 | 82 | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF PTU THERMAL INHIBITION LOGIC |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0001 | Yes | MR0001 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 19:07 | 9.2 | 2023-09-23 12:19 | 2023-09-23 13:19 | 8 | 82 |  | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF PTU THERMAL INHIBITION LOGIC | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291000-22-1 | 83 | MAIN/AUXILIARY POWER FUNCTIONAL CHECK OF HYDRAULIC FIRE SHUT OFF VALVES NOTE: INTERVAL: - TASK MAY BE PERFORMED AT OPPORTUNITY OF ENGINE REMOVAL P |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:20 | 0.46 | 2023-09-22 08:22 | 2023-09-22 09:22 | 2 | 83 |  | MAIN/AUXILIARY POWER FUNCTIONAL CHECK OF HYDRAULIC FIRE SHUT OFF VALVES NOTE: INTERVAL: - TASK MAY BE PERFORMED AT OPPORTUNITY OF ENGINE REMOVAL PROVIDED INTERVAL NOT EXCEEDED. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 291900-02-1 | 84 | MAIN AND AUXILIARY HYDRAULIC POWER FUNCTIONAL CHECK TO MONITOR INTERNAL LEAK RATE OF BLUE HYDRAULIC SYSTEM |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:26 | 0.69 | 2023-09-23 10:27 | 2023-09-23 11:27 | 2.5 | 84 |  | MAIN AND AUXILIARY HYDRAULIC POWER FUNCTIONAL CHECK TO MONITOR INTERNAL LEAK RATE OF BLUE HYDRAULIC SYSTEM | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 29 | 293400-01-1 | 85 | RESERVOIR PRESSURIZATION INDICATING OPERATIONAL CHECK OF RESERVOIR LOW AIR PRESSURE WARNING |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | mr0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-23 14:28 | 2023-09-23 15:28 | 1.1 | 85 |  | RESERVOIR PRESSURIZATION INDICATING OPERATIONAL CHECK OF RESERVOIR LOW AIR PRESSURE WARNING | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 31 | 313300-03-1 | 86 | DFDR SYSTEM INTERCONNECTION OPERATIONAL CHECK OF ULB |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.39 | 2023-09-22 07:57 | 2023-09-22 08:57 | 1.5 | 86 |  | DFDR SYSTEM INTERCONNECTION OPERATIONAL CHECK OF ULB | Hold | Pending Estimates |  | B2 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 31 | 315000-01-1 | 87 | CENTRAL WARNING SYSTEMS/ELECTRONIC INSTRUMENT SYSTEM (EIS) OPERATIONAL CHECK OF CORRECT OPERATION OF PFD-ND AND ECAM-ND MANUAL TRANSFER |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:20 | 0.46 | 2023-09-21 13:46 | 2023-09-21 14:46 | 1.3 | 87 |  | CENTRAL WARNING SYSTEMS/ELECTRONIC INSTRUMENT SYSTEM (EIS) OPERATIONAL CHECK OF CORRECT OPERATION OF PFD-ND AND ECAM-ND MANUAL TRANSFER | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 31 | 315000-02-1 | 88 | CENTRAL WARNING SYSTEMS/ELECTRONIC INSTRUMENT SYSTEM (EIS) OPERATIONAL CHECK OF CORRECT OPERATION OF EFIS AND ECAM DMC AUTOMATIC AND MANUAL TRANSFER |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | Yes | MR0032 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:32 | 0.92 | 2023-09-21 13:01 | 2023-09-21 14:01 | 1.3 | 88 |  | CENTRAL WARNING SYSTEMS/ELECTRONIC INSTRUMENT SYSTEM (EIS) OPERATIONAL CHECK OF CORRECT OPERATION OF EFIS AND ECAM DMC AUTOMATIC AND MANUAL TRANSFER | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 31 | 315000-04-1 | 89 | CENTRAL WARNING SYSTEMS/ELECTRONIC INSTRUMENT SYSTEM (EIS) OPERATIONAL CHECK OF DMC3 POWER SUPPLY TRANSFER WHEN BUSBAR 101XP IS LOST |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:20 | 0.46 | 2023-09-21 13:47 | 2023-09-21 14:47 | 1.3 | 89 |  | CENTRAL WARNING SYSTEMS/ELECTRONIC INSTRUMENT SYSTEM (EIS) OPERATIONAL CHECK OF DMC3 POWER SUPPLY TRANSFER WHEN BUSBAR 101XP IS LOST | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 321113-04-1 (LH) | 90 | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:56 | 1.84 | 2023-09-24 11:05 | 2023-09-24 12:05 | 4 | 90 |  | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE | Hold | Pending Estimates |  |  |  |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 321113-04-1 (RH) | 91 | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:56 | 1.84 | 2023-09-24 11:20 | 2023-09-24 12:31 | 4 | 91 |  | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE | Hold | Pending Estimates |  |  |  |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 323100-05-1 | 92 | NORMAL EXTENSION AND RETRACTION DETAILED INSPECTION OF NOSE GEAR DOOR OPERATING MECHANISM |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:28 | 0.78 | 2023-09-22 12:01 | 2023-09-22 13:01 | 3 | 92 |  | NORMAL EXTENSION AND RETRACTION DETAILED INSPECTION OF NOSE GEAR DOOR OPERATING MECHANISM | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 323100-06-1 | 93 | NORMAL EXTENSION AND RETRACTION BITE CHECK USING MCDU TO ENSURE "GEAR NOT DOWN FOR LANDING" WARNINGS OPERATIVE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-21 13:01 | 2023-09-21 14:01 | 1.5 | 93 |  | NORMAL EXTENSION AND RETRACTION BITE CHECK USING MCDU TO ENSURE "GEAR NOT DOWN FOR LANDING" WARNINGS OPERATIVE | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 324000-14-1 | 94 | WHEELS AND BRAKES FUNCTIONAL CHECK OF THE AUTOMATIC REACTIVATION OF THE NORMAL BRAKING MODE (PARKING BRAKE APPLIED) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 19:44 | 10.58 | 2023-09-23 09:17 | 2023-09-23 10:17 | 2.5 | 94 |  | WHEELS AND BRAKES FUNCTIONAL CHECK OF THE AUTOMATIC REACTIVATION OF THE NORMAL BRAKING MODE (PARKING BRAKE APPLIED) | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 324000-17-1 | 95 | WHEELS AND BRAKES FUNCTIONAL CHECK OF BRAKE ACCUMULATOR SYSTEM. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0001 | Yes | mr0001 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 16:06 | 2.27 | 2023-09-24 11:26 | 2023-09-24 12:26 | 4 | 95 |  | WHEELS AND BRAKES FUNCTIONAL CHECK OF BRAKE ACCUMULATOR SYSTEM. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 324300-01-3 | 96 | ALTERNATE BRAKING SYSTEM OPERATIONAL CHECK OF ALTERNATE BRAKING SYSTEM NOTE: TASK MAY BE ACCOMPLISHED AT BRAKE CHANGE. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | mr0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:44 | 1.38 | 2023-09-23 14:28 | 2023-09-23 15:28 | 2 | 96 |  | ALTERNATE BRAKING SYSTEM OPERATIONAL CHECK OF ALTERNATE BRAKING SYSTEM NOTE: TASK MAY BE ACCOMPLISHED AT BRAKE CHANGE. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 32 | 324500-01-2 | 97 | PARKING/ULTIMATE EMERGENCY BRAKING SYSTEM OPERATIONAL CHECK OF THE PARKING BRAKE SYSTEM |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | mr0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:56 | 1.84 | 2023-09-23 14:29 | 2023-09-23 15:29 | 2 | 97 |  | PARKING/ULTIMATE EMERGENCY BRAKING SYSTEM OPERATIONAL CHECK OF THE PARKING BRAKE SYSTEM | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 33 | 334800-01-1 | 98 | ANTI-COLLISION/STROBE LIGHTING VISUAL CHECK OF NEOL (NEAR END OF LIFE) ACTIVATION ON BEACON LIGHTS NOTE: - DEPENDING ON OPERATING ENVIRONMENT AND OP |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:19 | 0.46 | 2023-09-24 12:32 | 2023-09-24 13:32 | 2 | 98 |  | ANTI-COLLISION/STROBE LIGHTING VISUAL CHECK OF NEOL (NEAR END OF LIFE) ACTIVATION ON BEACON LIGHTS NOTE: - DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT OR MORE FREQUENT INITIAL INTERVAL MAY BE USED. | Hold | Pending Estimates |  | B2 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 34 | 341300-05-1 | 99 | AIR DATA OPERATIONAL CHECK OF THE 5-MINUTE TIME DELAY OF ADIRU 2 AND 3 POWER DISCONNECTION IN EMERGENCY CONFIGURATION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0038 | Yes | MR0038 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:20 | 0.46 | 2023-09-21 12:59 | 2023-09-21 13:59 | 1.5 | 99 |  | AIR DATA OPERATIONAL CHECK OF THE 5-MINUTE TIME DELAY OF ADIRU 2 AND 3 POWER DISCONNECTION IN EMERGENCY CONFIGURATION | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 34 | 341300-13-1 | 100 | Functional Test of the ADM Accuracy |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | FNC | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:28 | 0.85 | 2023-09-22 07:52 | 2023-09-22 09:00 | 4 | 100 |  | Functional Test of the ADM Accuracy | Hold | Pending Estimates |  | B2 |  |  | TASK | 1C+EOS | 1C+EOS
No | 34 | 342200-05-1 | 101 | STANDBY NAVIGATION SYSTEMS (INCLUDING ISIS) LOW RANGE LEAK TEST OF STANDBY PNEUMATIC CIRCUITS NOTE: PLANNING: - THIS TASK IS COVERED BY TASK 342200- |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:34 | 1.01 | 2023-09-24 09:44 | 2023-09-24 10:44 | 4 | 101 |  | STANDBY NAVIGATION SYSTEMS (INCLUDING ISIS) LOW RANGE LEAK TEST OF STANDBY PNEUMATIC CIRCUITS NOTE: PLANNING: - THIS TASK IS COVERED BY TASK 342200-02-1. | Hold | Pending Estimates |  | B2 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 34 | 344800-01-1 | 102 | GROUND PROXIMITY WARNING SYSTEM OPERATIONAL CHECK OF GROUND SELF TEST SYSTEM |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | Yes | MR0032 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:20 | 0.46 | 2023-09-21 13:02 | 2023-09-21 14:02 | 1.05 | 102 |  | GROUND PROXIMITY WARNING SYSTEM OPERATIONAL CHECK OF GROUND SELF TEST SYSTEM | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 35 | 353000-07-1 | 103 | PORTABLE OXYGEN DETAILED INSPECTION OF PORTABLE OXYGEN MASK |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0067 | Yes | MR0067 | No |  |  |  |  | 2023-09-11 15:07 | 2023-09-11 15:19 | 0.46 | 2023-09-21 13:49 | 2023-09-21 14:49 | 2 | 103 |  | PORTABLE OXYGEN DETAILED INSPECTION OF PORTABLE OXYGEN MASK | Hold | Pending Estimates |  | B2 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 36 | 361141-07-1 (LH) | 104 | IP BLEED CHECK VALVE REMOVE INTERMEDIATE PRESSURE BLEED CHECK VALVE FOR DETAILED INSPECTION. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:23 | 2.89 | 2023-09-21 13:14 | 2023-09-23 16:06 | 6 | 104 |  | IP BLEED CHECK VALVE REMOVE INTERMEDIATE PRESSURE BLEED CHECK VALVE FOR DETAILED INSPECTION. | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 36 | 361141-07-1 (RH) | 105 | IP BLEED CHECK VALVE REMOVE INTERMEDIATE PRESSURE BLEED CHECK VALVE FOR DETAILED INSPECTION. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:23 | 2.89 | 2023-09-22 07:51 | 2023-09-23 17:02 | 6 | 105 |  | IP BLEED CHECK VALVE REMOVE INTERMEDIATE PRESSURE BLEED CHECK VALVE FOR DETAILED INSPECTION. | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 38 | 384241-01-1 | 106 | AIR SUPPLY DETAILED INSPECTION OF COMPRESSOR INLET FILTER. NOTE: INTERVAL: - DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS F |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-22 12:00 | 2023-09-22 13:00 | 2.5 | 106 |  | AIR SUPPLY DETAILED INSPECTION OF COMPRESSOR INLET FILTER. NOTE: INTERVAL: - DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT OR MORE FREQUENT INITIAL INTERVAL MAY BE USED. | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 49 | 491300-B1-1 | 107 | FIRE SEALS GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS: - COMPARTMENT DOORS - FWD AND AFT FIRE WALLS - SIDE FIRE WALLS - UP |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:34 | 3.31 | 2023-09-22 13:55 | 2023-09-22 14:55 | 1.5 | 107 |  | FIRE SEALS GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS: - COMPARTMENT DOORS - FWD AND AFT FIRE WALLS - SIDE FIRE WALLS - UPPER FIRE WALL | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 49 | 491600-B1-1 | 108 | AIR INTAKE SYSTEM DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:29 | 0.8 | 2023-09-23 06:59 | 2023-09-23 13:56 | 4 | 108 |  | AIR INTAKE SYSTEM DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 49 | 498000-B1-1 | 109 | EXHAUST GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.27 | 2023-09-23 07:00 | 2023-09-23 13:57 | 4 | 109 |  | EXHAUST GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 52 | 521000-02-1 | 110 | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF DOOR SUSPENSION |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:34 | 1.01 | 2023-09-22 13:41 | 2023-09-22 14:41 | 2 | 110 |  | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF DOOR SUSPENSION | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 52 | 521000-03-1 | 111 | PASSENGER/CREW DOOR DETAILED INSPECTION OF DOOR SEALS NOTE: PLANNING: - TASK IS NOT APPLICABLE FOR DEACTIVATED PASSENGER/ CREW DOORS. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:24 | 0.64 | 2023-09-22 13:46 | 2023-09-22 14:46 | 1.2 | 111 |  | PASSENGER/CREW DOOR DETAILED INSPECTION OF DOOR SEALS NOTE: PLANNING: - TASK IS NOT APPLICABLE FOR DEACTIVATED PASSENGER/ CREW DOORS. | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 52 | 521000-04-1 | 112 | PASSENGER/CREW DOOR DETAILED INSPECTION OF PASSENGER/CREW DOOR FOR INTEGRITY AND GOOD ADJUSTMENT OF MECHANISMS (INCLUDING GIRT BAR) NOTE: PLANNING: |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:23 | 2.89 | 2023-09-22 07:53 | 2023-09-22 14:38 | 4 | 112 |  | PASSENGER/CREW DOOR DETAILED INSPECTION OF PASSENGER/CREW DOOR FOR INTEGRITY AND GOOD ADJUSTMENT OF MECHANISMS (INCLUDING GIRT BAR) NOTE: PLANNING: - ONLY FWD DOORS FOR POST 37807 (IF AFT DOORS FULLY DEACTIVATED). | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 52 | 521000-05-1 | 113 | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF LOCKING MECHANISM |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:36 | 1.1 | 2023-09-22 13:40 | 2023-09-22 14:40 | 2 | 113 |  | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF LOCKING MECHANISM | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 52 | 521000-06-1 | 114 | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF ESCAPE SLIDE RELEASE MECHANISM NOTE: PLANNING: - ONLY FWD DOORS FOR POST 37807 (IF AFT DOORS FULLY DEACTIV |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:56 | 1.84 | 2023-09-22 13:41 | 2023-09-22 14:41 | 2.5 | 114 |  | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF ESCAPE SLIDE RELEASE MECHANISM NOTE: PLANNING: - ONLY FWD DOORS FOR POST 37807 (IF AFT DOORS FULLY DEACTIVATED). | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 12 | 521121-02-1 | 115 | PASSENGER / CREW DOOR LUBRICATION OF SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM NOTE: TASK IS NOT APPLICABLE FOR DEACTIVATED PASSE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | LUB | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:51 | 1.65 | 2023-09-22 07:53 | 2023-09-23 10:13 | 3 | 115 |  | PASSENGER / CREW DOOR LUBRICATION OF SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM NOTE: TASK IS NOT APPLICABLE FOR DEACTIVATED PASSENGER/CREW DOORS | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 52 | 522100-01-1 | 116 | PASSENGER COMPARTMENT EMERGENCY EXIT OPERATIONAL CHECK OF UNLOCKING AND OPENING FROM INSIDE IN ARMED MODE. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:44 | 3.68 | 2023-09-22 13:40 | 2023-09-22 14:40 | 6 | 116 |  | PASSENGER COMPARTMENT EMERGENCY EXIT OPERATIONAL CHECK OF UNLOCKING AND OPENING FROM INSIDE IN ARMED MODE. | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 12 | 524100-02-1 | 117 | ACCESS DOORS LUBRICATION OF EXTERIOR AVIONIC COMPARTMENT DOOR HANDLE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | LUB | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:25 | 0.66 | 2023-09-22 11:17 | 2023-09-22 14:53 | 3 | 117 |  | ACCESS DOORS LUBRICATION OF EXTERIOR AVIONIC COMPARTMENT DOOR HANDLE | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 52 | 525111-07-1 | 118 | COCKPIT DOOR OPERATIONAL CHECK OF DEADBOLT |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:11 | 0.11 | 2023-09-22 13:47 | 2023-09-22 14:47 | 0.2 | 118 |  | COCKPIT DOOR OPERATIONAL CHECK OF DEADBOLT | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 531151-02-1 | 119 | DOOR STOP FITTINGS DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 17:14 | 2.1 | 2023-09-23 09:57 | 2023-09-23 10:57 | 2.5 | 119 |  | DOOR STOP FITTINGS DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 531176-02-1 | 120 | COCKPIT SIDE WINDOWS FRAMEWORK GENERAL VISUAL INSPECTION OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | GVI | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:23 | 1 | 2023-09-23 09:13 | 2023-09-23 10:13 | 1.2 | 120 |  | COCKPIT SIDE WINDOWS FRAMEWORK GENERAL VISUAL INSPECTION OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 531178-02-1 | 121 | COCKPIT WINDSHIELD RETAINERS GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:23 | 1 | 2023-09-23 09:14 | 2023-09-23 10:14 | 1.1 | 121 |  | COCKPIT WINDSHIELD RETAINERS GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 531182-02-1 | 122 | WINDSHIELD SLIDING WINDOW FRAME DETAILED INSPECTION OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 AND FR8 FRAMES, INTERNAL STRUCTURE FROM |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-12 01:15 | 10.12 | 2023-09-23 09:15 | 2023-09-23 10:15 | 12 | 122 |  | WINDSHIELD SLIDING WINDOW FRAME DETAILED INSPECTION OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 AND FR8 FRAMES, INTERNAL STRUCTURE FROM FR4 TO FR8 LH/RH. | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 531900-03-1 | 123 | FUSELAGE DRAINAGE OPERATIONAL CHECK OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL FROM OUTSIDE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:44 | 1.38 | 2023-09-22 13:54 | 2023-09-22 14:54 | 3.5 | 123 |  | FUSELAGE DRAINAGE OPERATIONAL CHECK OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL FROM OUTSIDE | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 532137-01-1 | 124 | FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION OF FORWARD CARGO DOOR CUTOUT PANELS, UPPER AND LOWER CORNERS, EXTERNAL SURFACE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:39 | 1.21 | 2023-09-21 13:36 | 2023-09-22 10:09 | 3 | 124 |  | FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION OF FORWARD CARGO DOOR CUTOUT PANELS, UPPER AND LOWER CORNERS, EXTERNAL SURFACE | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 533900-01-1 | 125 | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE HOLES IN PRESSURE FLOOR FROM MLG BAY |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-22 07:37 | 2023-09-22 08:37 | 2.5 | 125 |  | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE HOLES IN PRESSURE FLOOR FROM MLG BAY | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 534134-02-1 | 126 | DOOR STOP FITTINGS FR 66 AND 68 DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND FRAME 68, LH/RH |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:29 | 1.35 | 2023-09-22 13:48 | 2023-09-22 14:48 | 2.2 | 126 |  | DOOR STOP FITTINGS FR 66 AND 68 DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND FRAME 68, LH/RH. | Hold | Pending Estimates |  |  | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 535900-01-1 | 127 | FUSELAGE DRAINAGE OPERATIONAL CHECK OF SINGLE DRAIN PIPE AFT OF FR 70 FROM OUTSIDE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0060 | Yes | mr0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:11 | 0.11 | 2023-09-21 11:57 | 2023-09-23 15:30 | 0.5 | 127 |  | FUSELAGE DRAINAGE OPERATIONAL CHECK OF SINGLE DRAIN PIPE AFT OF FR 70 FROM OUTSIDE | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 53 | 535900-02-1 | 128 | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE AT BULK CARGO COMPARTMENT DOOR FROM OUTSIDE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:14 | 0.23 | 2023-09-22 07:38 | 2023-09-22 08:38 | 2.5 | 128 |  | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE AT BULK CARGO COMPARTMENT DOOR FROM OUTSIDE | Hold | Pending Estimates |  | B1 | 800 |  | TASK | 1C+EOS | 1C+EOS
No | 54 | 545900-L2-1 (LH) | 129 | PYLON DRAINAGE DETAILED INSPECTION OF RMF FINGER SEALS, BLOCK, KARMAN FAIRING AND NOSE FIRE SEALS. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:03 | 2.11 | 2023-09-23 10:53 | 2023-09-23 11:53 | 3 | 129 |  | PYLON DRAINAGE DETAILED INSPECTION OF RMF FINGER SEALS, BLOCK, KARMAN FAIRING AND NOSE FIRE SEALS. | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 54 | 545900-L2-1 (RH) | 130 | PYLON DRAINAGE DETAILED INSPECTION OF RMF FINGER SEALS, BLOCK, KARMAN FAIRING AND NOSE FIRE SEALS. |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:03 | 2.11 | 2023-09-22 13:01 | 2023-09-22 14:01 | 3 | 130 |  | PYLON DRAINAGE DETAILED INSPECTION OF RMF FINGER SEALS, BLOCK, KARMAN FAIRING AND NOSE FIRE SEALS. | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 12 | 561200-02-1 | 131 | SLIDING WINDOWS LUBRICATION OF COCKPIT SLIDING WINDOW TRACKS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | LUB | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:20 | 0.46 | 2023-09-23 09:55 | 2023-09-23 10:55 | 1.2 | 131 |  | SLIDING WINDOWS LUBRICATION OF COCKPIT SLIDING WINDOW TRACKS | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 78 | 781000-L1-1 (LH) | 132 | COLLECTOR/NOZZLE DETAILED INSPECTION OF INNER AND OUTER FINGER SEALS. NOTE: PLANNING: - CREDIT CAN BE TAKEN FROM THE ACCOMPLISHMENT OF THE DISCARD |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:51 | 1.65 | 2023-09-23 08:23 | 2023-09-23 09:47 | 3 | 132 |  | COLLECTOR/NOZZLE DETAILED INSPECTION OF INNER AND OUTER FINGER SEALS. NOTE: PLANNING: - CREDIT CAN BE TAKEN FROM THE ACCOMPLISHMENT OF THE DISCARD TASK (781000-L2-1). | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 78 | 781000-L1-1 (RH) | 133 | COLLECTOR/NOZZLE DETAILED INSPECTION OF INNER AND OUTER FINGER SEALS. NOTE: PLANNING: - CREDIT CAN BE TAKEN FROM THE ACCOMPLISHMENT OF THE DISCARD |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:51 | 1.65 | 2023-09-22 12:59 | 2023-09-22 14:00 | 3 | 133 |  | COLLECTOR/NOZZLE DETAILED INSPECTION OF INNER AND OUTER FINGER SEALS. NOTE: PLANNING: - CREDIT CAN BE TAKEN FROM THE ACCOMPLISHMENT OF THE DISCARD TASK (781000-L2-1). | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 20 | AGING OF CIRCUIT BREAKERS | 134 | AGING OF CIRCUIT BREAKERS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | INT | MAINT | Aircraft |  | POWER OFF | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:08 | 2 | 2023-09-22 11:29 | 2023-09-22 12:29 | 3 | 134 |  | PERFORM A MANUAL CYCLING OF ALL THERMAL CIRCUIT BREAKERS ON AND OFF (WITHOUT ANY LOAD) AS PER AMM 240000-200-004 | Not in hold | Not Required |  | B2 |  |  | TASK | 1C+EOS | 1C+EOS
No | 20 | WEAR LIMITS- BONDING LEADS | 135 | WEAR LIMITS ALLOWED FOR BONDING LEADS |  |  | Closed | 1C+EOS | 1 | LINE 2A | Not Required | INT | VCK | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:08 | 3 | 2023-09-24 14:51 | 2023-09-24 15:51 | 5 | 135 |  | CARRY OUT VISUAL INSPECTION TO DETERMINE WEAR LIMITS ALLOWED FOR BONDING LEADS FITTED ON MOVABLE SURFACES | Not in hold | Not Required |  | B2 |  |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-131-01-1 | 136 | FORWARD CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:21 | 0.52 | 2023-09-24 10:43 | 2023-09-24 11:43 | 3 | 136 |  | FORWARD CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-151-01-1 | 137 | AFT CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:21 | 0.5 | 2023-09-24 10:42 | 2023-09-24 11:42 | 3 | 137 |  | AFT CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-161-01-1 | 138 | BULK CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:21 | 0.5 | 2023-09-24 10:42 | 2023-09-24 11:42 | 2.5 | 138 |  | BULK CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-195-01-1 | 139 | HYDRAULIC COMPARTMENT AND FAIRINGS GENERAL VISUAL INSPECTION OF HYDRAULIC COMPARTMENT AND FAIRINGS (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1142 | Yes | MR1142 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:34 | 1.01 | 2023-09-24 10:43 | 2023-09-24 11:43 | 2.5 | 139 |  | HYDRAULIC COMPARTMENT AND FAIRINGS GENERAL VISUAL INSPECTION OF HYDRAULIC COMPARTMENT AND FAIRINGS (EWIS) | Hold | Pending Estimates |  | B1 | 100 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-200-02-1 | 140 | UPPER HALF OF FUSELAGE GENERAL VISUAL INSPECTION OF UPPER HALF OF FUSELAGE |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 23:32 | 19.32 | 2023-09-24 08:50 | 2023-09-24 09:50 | 20.5 | 140 |  | UPPER HALF OF FUSELAGE GENERAL VISUAL INSPECTION OF UPPER HALF OF FUSELAGE | Hold | Pending Estimates |  | B1 | 200 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-311-01-1 | 141 | AFT FUSELAGE TAIL SECTION GENERAL VISUAL INSPECTION OF AFT FUSELAGE TAIL SECTION (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:23 | 0.57 | 2023-09-23 12:45 | 2023-09-23 13:45 | 1.5 | 141 |  | AFT FUSELAGE TAIL SECTION GENERAL VISUAL INSPECTION OF AFT FUSELAGE TAIL SECTION (EWIS) | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-313-01-1 | 142 | TAIL CONE APU AIR INTAKE AREA GENERAL VISUAL INSPECTION OF TAIL CONE APU AIR INTAKE AREA (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.29 | 2023-09-23 12:46 | 2023-09-23 13:46 | 1.5 | 142 |  | TAIL CONE APU AIR INTAKE AREA GENERAL VISUAL INSPECTION OF TAIL CONE APU AIR INTAKE AREA (EWIS) | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-315-01-1 | 143 | TAIL CONE APU AND ACCESSORY COMPARTMENT GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:21 | 0.5 | 2023-09-23 12:46 | 2023-09-23 13:46 | 1.5 | 143 |  | TAIL CONE APU AND ACCESSORY COMPARTMENT GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-325-01-1 | 144 | VERTICAL STABILIZER TRAILING EDGE GENERAL VISUAL INSPECTION OF VERTICAL STABILIZER TRAILING EDGE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0060 | Yes | MR0060 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:24 | 0.64 | 2023-09-23 12:47 | 2023-09-23 13:47 | 6 | 144 |  | VERTICAL STABILIZER TRAILING EDGE GENERAL VISUAL INSPECTION OF VERTICAL STABILIZER TRAILING EDGE (EWIS) | Hold | Pending Estimates |  | B1 | 300 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-411-01-5 (LH) | 145 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:19 | 2.74 | 2023-09-23 15:16 | 2023-09-23 16:16 | 2.5 | 145 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-411-01-5 (RH) | 146 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 16:19 | 2.74 | 2023-09-23 16:03 | 2023-09-23 17:03 | 3 | 146 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-415-02-2 (LH) | 147 | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:44 | 1.4 | 2023-09-23 15:15 | 2023-09-23 16:15 | 2 | 147 |  | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-415-02-2 (RH) | 148 | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:44 | 1.4 | 2023-09-24 08:39 | 2023-09-24 09:39 | 3 | 148 |  | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-437-01-5 (LH) | 149 | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:23 | 0.59 | 2023-09-23 15:13 | 2023-09-23 16:13 | 2 | 149 |  | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-437-01-5 (RH) | 150 | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:23 | 0.59 | 2023-09-24 11:13 | 2023-09-24 12:13 | 2 | 150 |  | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-451-01-5 (LH) | 151 | THRUST REVERSER GENERAL VISUAL INSPECTION OF THRUST REVERSER (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:35 | 1.05 | 2023-09-24 07:52 | 2023-09-24 08:52 | 3 | 151 |  | THRUST REVERSER GENERAL VISUAL INSPECTION OF THRUST REVERSER (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-451-01-5 (RH) | 152 | THRUST REVERSER GENERAL VISUAL INSPECTION OF THRUST REVERSER (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:35 | 1.05 | 2023-09-24 11:15 | 2023-09-24 12:15 | 3 | 152 |  | THRUST REVERSER GENERAL VISUAL INSPECTION OF THRUST REVERSER (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-471-02-2 (LH) | 153 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:39 | 1.21 | 2023-09-23 15:14 | 2023-09-23 16:14 | 2 | 153 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-471-02-2 (RH) | 154 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:39 | 1.21 | 2023-09-24 08:46 | 2023-09-24 09:46 | 2 | 154 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-475-01-2 (LH) | 155 | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:28 | 0.78 | 2023-09-23 15:17 | 2023-09-23 16:17 | 3 | 155 |  | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-475-01-2 (RH) | 156 | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:28 | 0.78 | 2023-09-24 08:42 | 2023-09-24 09:42 | 3 | 156 |  | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 | 400 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-500-03-1 (LH) | 157 | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:27 | 0.75 | 2023-09-24 07:50 | 2023-09-24 08:50 | 2.5 | 157 |  | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-500-03-1 (RH) | 158 | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:27 | 0.75 | 2023-09-24 11:12 | 2023-09-24 12:12 | 2.5 | 158 |  | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-531-01-1 (LH) | 159 | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:16 | 0.32 | 2023-09-24 07:54 | 2023-09-24 08:54 | 4 | 159 |  | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-531-01-1 (RH) | 160 | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:16 | 0.32 | 2023-09-22 11:20 | 2023-09-24 09:35 | 4 | 160 |  | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-532-01-1 (LH) | 161 | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:16 | 0.32 | 2023-09-24 07:53 | 2023-09-24 08:53 | 4 | 161 |  | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-532-01-1 (RH) | 162 | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:16 | 0.32 | 2023-09-24 08:38 | 2023-09-24 09:38 | 4 | 162 |  | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-533-01-1 (LH) | 163 | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:16 | 0.32 | 2023-09-24 07:55 | 2023-09-24 08:55 | 4 | 163 |  | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-533-01-1 (RH) | 164 | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:16 | 0.32 | 2023-09-22 11:16 | 2023-09-24 09:37 | 4 | 164 |  | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-573-01-1 (LH) | 165 | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.27 | 2023-09-23 15:12 | 2023-09-23 16:12 | 2 | 165 |  | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-573-01-1 (RH) | 166 | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:15 | 0.27 | 2023-09-24 08:33 | 2023-09-24 09:33 | 2 | 166 |  | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-574-01-1 (LH) | 167 | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:22 | 0.55 | 2023-09-24 07:49 | 2023-09-24 08:49 | 2.5 | 167 |  | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-574-01-1 (RH) | 168 | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:22 | 0.55 | 2023-09-24 08:34 | 2023-09-24 09:34 | 2.5 | 168 |  | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-590-01-1 (LH) | 169 | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.4 | 2023-09-24 07:51 | 2023-09-24 08:51 | 3 | 169 |  | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-590-01-1 (RH) | 170 | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:18 | 0.4 | 2023-09-24 08:32 | 2023-09-24 09:32 | 3 | 170 |  | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) | Hold | Pending Estimates |  | B1 | 500 |  | TASK | 1C+EOS | 1C+EOS
No | 5 | ZL-734-01-1 | 171 | MAIN LANDING GEAR MAIN DOORS GENERAL VISUAL INSPECTION OF MAIN LANDING GEAR MAIN DOORS (EWIS) |  |  | Closed | 1C+EOS | 1 | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1089 | Yes | MR1089 | No |  |  |  |  | 2023-09-11 15:08 | 2023-09-11 15:22 | 0.55 | 2023-09-24 08:40 | 2023-09-24 09:40 | 2 | 171 |  | MAIN LANDING GEAR MAIN DOORS GENERAL VISUAL INSPECTION OF MAIN LANDING GEAR MAIN DOORS (EWIS) | Hold | Pending Estimates |  | B1 | 700 |  | TASK | 1C+EOS | 1C+EOS
No | 20 | AWR23/002844/0923 | 172 | ILB |  |  | Pre-Closed |  |  | LINE 2A | Pending Mech&Insp | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes |  | Yes |  | No |  |  |  |  | 2023-09-14 12:11 | 2023-09-14 13:11 | 1 | 2023-09-14 11:11 | 2023-09-20 15:59 | 0 | 172 |  | ILB | Hold | Pending Estimates |  |  |  |  | TASK
No | 20 | AWR23/002845/0923 | 173 | ILB |  |  | Pre-Closed |  |  | LINE 2A | Pending Mech&Insp | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes |  | Yes |  | No |  |  |  |  | 2023-09-14 12:11 | 2023-09-14 13:11 | 1 | 2023-09-14 11:11 | 2023-09-20 15:59 | 0 | 173 |  | ILB | Hold | Pending Estimates |  |  |  |  | TASK
No | 53 | AWR23/002846/0923 | 174 | CARRY OUT EXTERNAL HFEC INSPECTION AS PER NTM TASK 51-10-08.FOR DENT REFER EO-04 |  | EDDY CURRENT INSPECTION CARRIED OUT ON AFT FUSELAGE SKIN PLATE BEHIND L2 DOOR BETWEEN FRAME 68 AND 69 & STRINGER 19LH AND 20LH. NO CRACK INDICATION OBSERVED DURING THE INSPECTION. NIL FINDINGS. FOR DETAILS REFER NDT REPORT NO: GAT/NDT/13848 | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | mr0001 | Yes | mr0001 | No |  |  |  |  | 2023-09-14 12:11 | 2023-09-14 13:11 | 1 | 2023-09-14 11:11 | 2023-09-24 12:24 | 2 | 174 |  | CARRY OUT EXTERNAL HFEC INSPECTION AS PER NTM TASK 51-10-08.FOR DENT REFER EO-04 | Hold | Pending Estimates |  |  |  |  | TASK
No | 53 | AWR23/002847/0923 | 175 | CARRY OUT EXTERNAL LFEC INSPECTION AS PER NTM TASK 51-10-16.FOR DENT REFER EO-05 |  | EDDY CURRENT LFEC TESTING CARRIED OUT ON AFTFUSELAGE PLATE BEHIND L2 DOOR BETWEEN FRAME 68 AND 69 & STRINGER 19LH AND 20LH. NO CRACK INDICATION OBSERVED DURING INSPECTION. NIL FINDINGS. FOR DETAILS REFER NDT REPORT NO: GAT/NDT/13849 | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | mr0001 | Yes | mr0001 | No |  |  |  |  | 2023-09-14 12:10 | 2023-09-14 13:10 | 1 | 2023-09-14 11:11 | 2023-09-24 12:24 | 2 | 175 |  | CARRY OUT EXTERNAL LFEC INSPECTION AS PER NTM TASK 51-10-16.FOR DENT REFER EO-05 | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | CARPET REPLACEMENT | 176 | CARRY OUT CARPET REPLACEMENT AS PER CUSTOMER REQUEST |  | CARRIED OUT REPLACEMENT OF AISLE CARPET AND FRONT ROW CARPET WITH NEW ONE AS PER AMM TASK 25-28-41-400-001-A, REV-72, DATED: 01-AUG-2023. | Closed |  |  | LINE 2A | Not Required | Non Routine | RPL | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-14 12:43 | 2023-09-14 13:43 | 1 | 2023-09-14 11:43 | 2023-09-24 13:02 | 8 | 176 |  | CARRY OUT CARPET REPLACEMENT AS PER CUSTOMER REQUEST | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | NTF REPLACEMENT | 177 | CARRY OUT REPLACEMENT OF NTF AS PER CUSTOMER REQUEST |  | CARRIED OUT REPLACEMENT OF NTF IN FWD UTILITY AREA WITH NEW ONE AS PER AMM TASK 25-28-42-400-001-A, REV-72, DATED: 01--AUG-2023. | Closed |  |  | LINE 2A | Not Required | Non Routine | RPL | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-14 12:43 | 2023-09-14 13:43 | 1 | 2023-09-14 11:43 | 2023-09-24 13:02 | 8 | 177 |  | CARRY OUT REPLACEMENT OF NTF AS PER CUSTOMER REQUEST | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | VINYL REPLACEMENT | 178 | CARRY OUT VINYL REPLACEMENT AS PER CUSTOMER REQUEST |  | 1. CARRIED OUT REMOVAL OF FWD CABIN PARTITION PANEL AS PER AMM TASK 25-26-42 -000-001-A,REV 72, DATED 01-AUG-2023 FOR VINYLE REPLACEMENT. 2. POST VINYLE REPLACEMENT CARRIED OUT INSTALLATION OF FWD CABIN PARTITION PANELS AS PER AMM TASK 25- 26-42-400-001-A, REV 72, DATED: 01-AUG-2023. FOUND SATISFACTORY. | Closed |  |  | LINE 2A | Not Required | Non Routine | RPL | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-14 12:43 | 2023-09-14 13:43 | 1 | 2023-09-14 11:43 | 2023-09-24 13:02 | 16 | 178 |  | CARRY OUT VINYL REPLACEMENT AS PER CUSTOMER REQUEST | Hold | Pending Estimates |  |  |  |  | TASK
No | 12 | ISSUE OF COMMERCIAL ITEMS | 179 | ISSUE OF COMMERCIAL ITEMS FOR AIRCRAFT MAINTENANCE |  |  | Closed |  |  | LINE 2A | Not Required | INT | CLN | Aircraft |  | POST DOCK | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-21 07:24 | 2023-09-21 07:54 | 0.5 | 2023-09-21 06:24 | 2023-09-24 13:34 | 3 | 179 |  | ISSUE OF COMMERCIAL ITEMS FOR AIRCRAFT MAINTENANCE | Hold | Pending Estimates |  |  |  |  | TASK
No | 53 | AIRCRAFT ARRIVAL INSPECTION | 180 | CARRY OUT AIRCRAFT ARRIVAL INSPECTION |  |  | Closed |  |  | LINE 2A | Not Required | INT | GVI | Aircraft |  | PRE DOCK | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-09-21 07:26 | 2023-09-21 08:26 | 2 | 2023-09-21 06:26 | 2023-09-24 15:50 | 3 | 180 |  | CARRY OUT AIRCRAFT ARRIVAL INSPECTION AS PER GAT INSPECTION SCHEDULE | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | AWR23/003071/0923 | 191 | CARRY OUT CABIN REFURBISHMENT. |  | CARRIED OUT CABIN REFURBISHMENT AS PER CUSTOMER REQUEST. 1. CARRIED OUT REMOVAL OF ALL WALL MOUNTED CABIN ATTENDANT SEATS FOR PAINTING AS PER AMM TASK 25-22-41-000-001-A, REV 72, DATED 01-AUG-2023. REFER FOLLOWING CWO FOR CA SEATS PAINTING DETAILS:- CWO23/000388/0923 CWO23/000389/0923 CWO23/000390/0923 CWO23/000391/0923 CWO23/000392/0923 2. CARRIED OUT REMOVAL OF DECORATIVE COVER OF ESCAPE SLIDE/RAFT OF ALL THE PASSENGER DOORS AS PER AMM TASK 25-62-00-000-801-A, REV-72, DATED 01-AUG-2023. REFER CWO23/000396/0923 FOR PAINTING DETAILS. ACTION: 1. CARRIED OUT INSTALLATION OF WALL MOUNTED CABIN ATTENDANT SEATS AS PER AMM TASK 25-22-41-400-001-A, REV 72, DATED 01-AUG-2023. FOUND SATISFACTORY. 2. CARRIED OUT INSTALLATION OF DECORATIVE COVER OF ESCAPE SLIDE/RAFT OF ALL THE PASSENGER DOORS AS PER AMM TASK 25-62-00-400-801-A, REV-72, DATED 01-AUG-2023. | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-21 10:53 | 2023-09-21 11:53 | 1 | 2023-09-21 09:53 | 2023-09-24 13:04 | 24 | 191 |  | CARRY OUT CABIN REFURBISHMENT. | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | AWR23/003074/0923 | 196 | AS PER CUSTOMER REQUEST, CARRY OUT CA SEAT PAINTING. |  | 1. CARRIED OUT REMOVAL OF ALL WALL MOUNTED CABIN ATTENDANT SEATS FOR PAINTING AS PER AMM TASK 25-22-41-000-001-A, REV 72, DATED 01-AUG-2023. REFER FOLLOWING CWO FOR PAINTING DETAILS:- CWO23/000388/0923 CWO23/000389/0923 CWO23/000390/0923 CWO23/000391/0923 CWO23/000392/0923 2. CARRIED OUT INSTALLATION OF WALL MOUNTED CABIN ATTENDANT SEATS AS PER AMM TASK 25-22-41-400-001-A, REV 72, DATED 01-AUG-2023. FOUND SATISFACTORY. | Pre-Closed |  |  | LINE 2A | Pending Mech&Insp | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes |  | Yes |  | No |  |  |  |  | 2023-09-21 12:24 | 2023-09-21 13:24 | 1 | 2023-09-21 11:25 | 2023-09-23 07:15 | 0 | 196 |  | AS PER CUSTOMER REQUEST, CARRY OUT CA SEAT PAINTING. | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | AWR23/003076/0923 | 199 | CARRY OUT RADOME PAINTING |  | TASK CANCELLED, UNABLE TO PRE-CLOSE | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR0001 | Yes | MR0001 | No |  |  |  |  | 2023-09-21 14:17 | 2023-09-21 15:17 | 1 | 2023-09-21 13:17 | 2023-09-24 12:29 | 0 | 199 |  | CARRY OUT RADOME PAINTING | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | AWR23/003078/0923 | 207 | CARRY OUT COCKPIT CARPET REPLACEMENT AS PER CUSTOMER REQUEST. |  | 1. CARRIED OUT REPLACEMENT OF COCKPIT FLOOR CARPET WITH NEW ONE AS PER AMM TASK 25-28-41-000-001-A, REV 72, DATED 01-AUG-2023. | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR1097 | Yes | MR1097 | No |  |  |  |  | 2023-09-22 09:48 | 2023-09-22 10:48 | 1 | 2023-09-22 08:48 | 2023-09-24 13:03 | 6 | 207 |  | CARRY OUT COCKPIT CARPET REPLACEMENT AS PER CUSTOMER REQUEST. | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | AWR23/003080/0923 | 211 | CARRY OUT EXTERNAL PAINT TOUCH UP. |  | CARRIED OUT EXTERNAL PAINT TOUCHUPS AS PER SRM 51-75-12-911-002 REV NO: 37 DATED AUG 01/2023.AND FOUND SATISFACTORY. | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR1155 | Yes | MR1155 | No |  |  |  |  | 2023-09-22 14:39 | 2023-09-22 15:39 | 1 | 2023-09-22 13:39 | 2023-09-23 16:46 | 15 | 211 |  | CARRY OUT EXTERNAL PAINT TOUCH UP. | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | AWR23/003086/0923 | 212 | AS PER CUSTOMER REQUEST, CARRY OUT WEEKLY INSPECTION. |  | AS PER CUSTOMER REQUEST, CARRIED OUT WEEKLY INSPECTION AS PER APPROVED SCHEDULE IGO/E&M/APPROVAL/INSP.SCH/178 DATED 16.11.2022. FOUND SATISFACTORY. | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-09-23 11:12 | 2023-09-23 12:12 | 1 | 2023-09-23 10:12 | 2023-09-24 14:57 | 8 | 212 |  | AS PER CUSTOMER REQUEST, CARRY OUT WEEKLY INSPECTION. | Hold | Pending Estimates |  |  |  |  | TASK