## Sheet1
DeleteFlag | Type | Log Item # | ATA # | Description | Corrective Action | Discrepancy # | Action | Status | Source Task/Discrep. # | Source Tracking # | Work Center # | Sign Off Status | Contract Classification | Category | Exe. Phase | Exec. Category | Part Required? | Corrosion Related? | Major Item? | Repeat? | Part # | Serial # | Position Code | Part Description | Radio Communication | Reported By | Reported Date | Mech Req? | Mech Sign Off | Mech Skill # | Insp Req? | Insp Sign Off | Insp Skill # | RII Req? | RII Sign Off | RII Skill # | Addl. Sign Off | Add New Sign Off Comments | Previous Sign Off Comments | Planned Start Date | Planned End Date | Est. Man Hrs. | Actual Start Date | Actual End Date | Actual Man Hrs. | Seq # | Tracking # | Source Tracking # | Hold Status | Estimation Status | File Name | Skill # | Zone # | Work Area # | Deferral FH | Deferral FC | Deferral Parameter | Deferral Value | Deferral Calendar Value | Deferral Calendar | Deferral Item # | Deferral Type | Reason for Deferral | Auth. Ref. # | Message Center
No | MIREP | HMV23/000043/0823/1 | 33 | DURING ARRIVAL INSPECTION OBSERVED 1. RH NAV POSITION LIGHT VERY DIM IN POSITION 02 AND NEAR END OF LIFE LIGHT IS BLINKING. 2. LAMP ITEM NO 24 IN SPARE BULB BOX MISSING. 3. QTY 03 LAMPS U/S IN AVIONICS COMPARTMENT 80VU AND 90VU AT LOCATIONS 6LS, 7LS AND 9LS. 4. LH AND RH NAVIGATION LIGHTS GLAZING PANELS ERRODED. 5. RH STROBE GLAZING PANEL SEALANT PEELED OFF. | 1. RH NAV POSITION LIGHT TROUBLESHOOTING CARRIED OUT AS PER TSM TASK 33-41-00-810-803-A REV 72, DT 01/08/2023. RH NAV POSITION LIGHT ASSY REPLACED AS THE LIGHT IS VERY DIM AS PER AMM 33-41-11-000-802-A AND 33-41-11-400-802-A REV 72, DT 01/08/2023. POST INSTALLATION CHECKS CARRIED OUT. FOUND SATISFACTORY. LIGHT ASSY ON/OFF PN: 727-1154-02 ON SN: S18328195 OFF SN: S19468684 2. LAMP PN: ABS1680-01 PLACED AT ITEM 24 IN SPARE BULB BOX. 3. AVIONICS COMPARTMENT LIGHT LAMP AT LOCATIONS 6LS, 7LS AND 9LS REPLACED AS PER AMM 33-35-11-000-002-A AND 33-35-11-400-002-A REV 72, DT 01/08/2023. OPERATIONAL TEST CARRIED OUT. FOUND SATISFACTORY. LAMP PN: NSA933239-2232 QTY : 04 4. LH AND RH NAVIGATION LIGHT GLAZING PANEL REPLACED AS PER AMM 57-37-13-000-801-A AND 57-37-13-400-801-A REV 72, DT 01/08/2023. LH NAVIGATION LIGHT GLAZING PANEL ON PN: D5735012100000 QTY : 01 OFF PN: D5735693700200 RH NAVIGATION LIGHT GLAZING PANEL PN: D5735012100100 QTY : 01 OFF PN: D5735693700300 5. RH STROBE GLAZING PANEL SEALANT REAPPLIED AS PER AMM 57-37-13-000-802-A AND 57-37-13-000-802-A 57-37-13-400-802-A REV 72, DT 01/08/2023. | HMV23/000043/0823/1 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 117 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1090 | 2023-08-25 10:08 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 11:31 | 6 | 2023-08-25 12:44 | 2023-08-28 14:50 | 16 | 118 | 118 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000043/0823/2 | 25 | CARRY OUT CA SEATS AND DOOR TRIMS (QTY49) PAINTING DUE CUSTOMER REQUEST. 1.CARRY OUT FWD ,AFT CA SEATS REMOVAL AND INSTALLATION 2.CARRY OUT FWD DOOR TRIMS,FWD AND AFT DOOR SURROUNDING TRIMS (QTY49) REMOVAL AND INSTALLATION | 1.FWD AND AFT WALL MOUNTED CABIN ATTENDENT SEATS REMOVED AND SAME SEATS INSTALLED BACK AS PER AMM 25-22-41-000-001-A/25-22-41-400-001-A REV 72 DT 01.08.2023 FWD I/B SEAT ON/OFF P/N:2428-82JE03A0DL ON/OFF S/N:7154-2428 FWD O/B SEAT ON/OFF P/N:2428-82ME03A0DL ON/OFF S/N:7113-2428 AFT CA SEAT(RH) ON/OFF P/N:2431-82PH00C0DL ON/OFF S/N:1027-2431 REFER CWO S FOR PAINTING DETAILS CWO23/000198/0823 CWO23/000199/0823 CWO23/000197/0823 FWD DOOR TRIMS,FWD AND AFT DOOR SURROUNDING TRIMS (QTY49)REMOVED AND SAME TRIMS INSTALLED BACK AS PER MPD CARD 521121-02-1 REV 72 DT 01.08.2023 REFER CWO FOR PAINTING DETAILS CWO23/000212/0823 | HMV23/000043/0823/2 | Close | Closed | AWR23/002577/0823 | 119 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | CT0536 | 2023-08-25 10:58 | Yes | CT0536 |  | Yes | CT0536 |  | No | [5 empty] | 2023-08-25 10:58 | 2023-08-25 11:58 | 4 | 2023-08-27 14:11 | 2023-08-28 16:24 | 12 | 120 | 120 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000043/0823/3 | 53 | DURING ARRIVAL INSPECTION OBSERVED DELAMINATION ON FWD CARGO FLOOR PANELS 131AF,131EF,131FF,131JF. 1)REMOVE FWD CARGO FLOOR PANEL 131AF,131EF,131FF,131JF FOR FABRICATION. 2) INSTALL FLOOR PANEL 131AF,131EF,131FF,131JF POST FABRICATION. 3) SEALS MISSING ON SOME FWD CARGO FLOOR PANELS. 4) SEVERAL HARDWARE FOUND MISSING ON FWD CARGO SIDEWALL AND CEILING PANELS. | 1)REMOVED FWD CARGO FLOOR PANEL 131AF,131EF,131FF,131JF FOR FABRICATION IAW AMM 53-22-14-000-001-A, REV72, DT: 01 AUG23 2) INSTALLED FWD CARGO FLOOR PANELS 131AF,131EF,131FF,131JF POST FABRICATION IAW AMM53-22-14-400-001-A, REV72, DT: 01 AUG23. REFER CWO FOR DETAILS. i)131AF: CWO23/000202/0803 ii)131EF: CWO23/000203/0803 iii)131FF: CWO23/000204/0803 iv) 131JF: CWO23/000210/0803 3)FWD CARGO FLOOR PANEL SEALS INSTALLED IAW AMM 53-22-14-400-802-A, REV72, DT: 01 AUG23 4) MISSING HARDWARE INSTALLED ON FWD CARGO SIDEWALL AND CEILING PANELS. | HMV23/000043/0823/3 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 117 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1546 | 2023-08-25 10:59 | Yes | MR1546 |  | Yes | MR1546 |  | No | [5 empty] | 2023-08-25 10:59 | 2023-08-25 11:59 | 8 | 2023-08-25 18:56 | 2023-08-28 16:40 | 8 | 121 | 121 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000043/0823/4 | 20 | DURING PHYSICAL INSPECTION OF BONDING LEADS, OBSERVED FOLLOWING JUMPERS BROKEN: 1. NLG DOOR QTY: 04 2. LH MLG DOOR QTY : 03 3. RH MLG DOOR QTY : 02 4. TOILET SERVICE DOOR QTY : 02 5. WATER SERVICE DOOR QTY :02 6. RH WING FLAP TRACK FAIRING #2 QTY: 01 7. RH ELEVATOR QTY : 04 8. RUDDER QTY : 01 | BONDING JUMPERS AT FOLLOWING LOCATIONS REPLACED AS PER AMM 20-28-00-912-802-A 57-37-13-000-802-A 1. NLG DOOR QTY: 04 2. LH MLG DOOR QTY : 03 3. RH MLG DOOR QTY : 02 4. TOILET SERVICE DOOR QTY : 02 5. WATER SERVICE DOOR QTY :02 6. RH WING FLAP TRACK FAIRING #2 QTY: 01 7. RH ELEVATOR QTY : 04 8. RUDDER QTY : 01 SECURITY OF INSTALLATION AND POST INSTALLATION TESTS CARRIED OUT. FOUND SATISFACTORY. | HMV23/000043/0823/4 | Close | Closed | WEAR LIMITS- BONDING LEADS | 105 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1090 | 2023-08-25 10:58 | Yes | MR1090 |  | Yes | MR1090 |  | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 11:31 | 30 | 2023-08-25 12:45 | 2023-08-28 14:14 | 24 | 122 | 122 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000043/0823/5 | 53 | DURING ARRIVAL INSPECTION OBSERVED DELAMINATION ON AFT CARGO FLOOR PANELS 151SG,151DF,151GF, 51LF, 151PF. 1)REMOVE AFT CARGO FLOOR PANELS 151SG,151DF,151GF, 51LF, 151PF FOR FABRICATION. 2) INSTALL AFT CARGO FLOOR PANELS 151SG,151DF,151GF, 51LF, 151PF POST FABRICATION. 3) SEVERAL HARDWARE FOUND MISSING ON AFT CARGO SIDEWALL AND CEILING PANELS. | 1)REMOVED AFT CARGO FLOOR PANELS 151SG,151DF,151GF, 51LF, 151PF FOR FABRICATION IAW AMM 53-42-14-000-001-A, REV72, DT: 01 AUG23 2) INSTALLED AFT CARGO FLOOR PANELS 151SG,151DF,151GF, 51LF, 151PF.POST FABRICATION IAW AMM53-42-14-400-001-A, REV72, DT: 01 AUG23. REFER CWO FOR DETAILS. i)151SG: CWO23/000208/0803 ii)151DF: CWO23/000205/0803 iii)151GF: CWO23/000206/0803 iv)151LF: CWO23/000209/0803 v) 151PF: CWO23/000207/0803 3) MISSING HARDWARE INSTALLED ON AFT CARGO SIDEWALL AND CEILING PANELS. | HMV23/000043/0823/5 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 117 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1546 | 2023-08-25 11:03 | Yes | MR1546 |  | Yes | MR1546 |  | No | [5 empty] | 2023-08-25 11:03 | 2023-08-25 12:03 | 8 | 2023-08-25 19:39 | 2023-08-28 17:42 | 8 | 123 | 123 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000043/0823/6 | 57 | WHILE ARRIVAL INSPECTION FOUND DENT ON LH WING SLAT #2 (P/N-D5746092000400, S/N-SA7202688) TOP SKIN BETWEEN I/B CLOSURE RIB AND WFX 4920 . SAME TO BE ASSESSED. | SERVICEABLE SLAT #2 OF LH WING PROVIDED BY INDIGO. FOR DETAILS REFER IRC:HMV23/000043/0823/9. | HMV23/000043/0823/6 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 117 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR0218 | 2023-08-25 11:38 | Yes | MR0049 | B1 | Yes | MR0049 | B1 | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 18:23 | 4 | 2023-08-28 16:29 | 2023-08-28 22:19 | 5 | 124 | 124 |  | Hold | Pending Estimates |  |  | 500 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/7 | 51 | REF TO IGO EO-4279 DENT ON RH WING SLAT #2 NOSE TOP SKIN. SAME TO BE REMOVED AS PER AMM 27-84-64-000-001-A ,REV 72,DT-01AUG23 FOR PERMANENT REPAIR P/N:D5746092000500, S/N:SA7202489. | CARRIED OUT REMOVAL OF RH WING SLAT NO#2 AS PER AMM 27-84-64-000-001-A,REV72,DT-01 AUG 2023. P/N:D5746092000500, S/N: SA7202489 | HMV23/000043/0823/7 | Close | Closed | AWR23/002555/0823 | 112 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1085 | 2023-08-25 11:48 | Yes | MR1085 |  | Yes | MR1085 |  | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 11:31 | 4 | 2023-08-25 13:04 | 2023-08-29 00:36 | 5 | 125 | 125 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/8 | 57 | REMOVAL OF LH WING SLAT #2 (P/N-D5746092000400, S/N-SA7202688)TO BE CARRIED OUT FOR REPAIR. | REMOVAL OF LH WING SLAT #2 (P/N-D5746092000400, S/N-SA7202688) CARRIED OUT AS PER AMM27-84-64-000-001-A,REV72,1 AUG2023. | HMV23/000043/0823/8 | Close | Closed | HMV23/000043/0823/6 | 124 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR0218 | 2023-08-25 11:53 | Yes | MR0218 |  | Yes | MR0218 |  | No | [5 empty] | 2023-08-24 14:37 | 2023-08-25 13:07 | 6 | 2023-08-25 13:05 | 2023-08-25 14:36 | 5 | 126 | 126 |  | Hold | Pending Estimates |  |  | 500 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/9 | 57 | POST REPAIR INSTALLATION OF LH WING SLAT #2(P/N-D5746092000400, S/N-SA7202688) TO BE CARRIED OUT . | SERVICEABLE SLAT #2 OF LH WING PROVIDED BY INDIGO AND SAME LH WING SLAT #2 INSTALLED AS PER AMM27-84-64-400-002-A,REV72, 1 AUG2023. (ON P/N-D5746092000400,ON S/N-SA10152) | HMV23/000043/0823/9 | Close | Closed | HMV23/000043/0823/6 | 124 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR0218 | 2023-08-25 11:55 | Yes | MR0049 | b1 | Yes | MR0049 | B1 | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 18:23 | 10 | 2023-08-25 13:07 | 2023-08-28 22:19 | 10 | 127 | 127 |  | Hold | Pending Estimates |  |  | 500 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/10 | 51 | POST REPAIR OF RH WING SLAT NO#2(P/N:D5746092000500, S/N: SA7202489) .SAME TO BE INSTALLED AS PER AMM 27-84-64-400-001-A, REV 72, DT-01AUG2023 | CARRIED OUT INSTALLATION OF RH WING SLAT #2 AS PER AMM 27-84-64-400-002-A,REV72,1 AUG2023.SECURITY OF INSTALLATION CHECKED FOUND SATISFACTORY. | HMV23/000043/0823/10 | Close | Closed | AWR23/002555/0823 | 112 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1085 | 2023-08-25 12:03 | Yes | MR1097 | B1 | Yes | MR1097 |  | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 18:23 | 6 | 2023-08-27 15:13 | 2023-08-28 00:47 | 16 | 128 | 128 |  | Hold | Pending Estimates |  |  | 600 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/11 | 57 | OPERATIONAL TEST OF SLAT#2 (LH & RH) WING TO BE CARRIED OUT AS PER AMM 27-84-00-710-001,REV 72, 1AUG 2023. | POST INSTALLATION OF #2 LH AND RH WING SLATS, OPERATIONAL TEST CARRIED OUT AS PER AMM 27-84-00-710-001, REV 72 DTD AUG 01/2023. FOUND SATISFACTORY. | HMV23/000043/0823/11 | Close | Closed | HMV23/000043/0823/9 | 127 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR0218 | 2023-08-25 12:05 | Yes | MR0049 | B1 | Yes | MR0049 | B1 | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 18:23 | 4 | 2023-08-28 22:19 | 2023-08-28 22:19 | 1.1 | 129 | 129 |  | Hold | Pending Estimates |  |  | 500 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/12 | 0 | WHILE ARRIVAL INSPECTION OBSERVED RH WING SLAT#5 OUTBOARD WEATHER SEAL ERODED.SAME TO BE REPLACED. | CARRIED OUT INSTALLATION OF RH WING SLAT #5 OUT BOARD WEATHER SEAL AS PER STANDARD PRACTICES 20-21-11-911-001-A, REV 72, DT-01 AUG 2023.SECURITY OF INSTALLATION CHECK FOUND SATISFACTORY. | HMV23/000043/0823/12 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 117 | LINE 2A | Signed Off | DISC-INTERNAL TASK | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1085 | 2023-08-25 12:07 | Yes | MR1085 |  | Yes | MR1085 |  | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 11:31 | 4 | 2023-08-27 13:58 | 2023-08-28 14:26 | 2 | 130 | 130 |  | Hold | Pending Estimates | [9 empty] | Hours
No | MIREP | HMV23/000043/0823/13 | 23 | DURING ARRIVAL CHECK OBSERVED ON VERTICAL STABILIZER QTY 01 AND HORIZONTAL STABILIZER ( RH) QTY 2 STATIC DISCHARGERS TIP DAMAGE. | CARRIED OUT REPLACEMENT OF STATIC DISCHARGERS WITH SERVICEABLE AS PER AMM TASK 23-61-41-000-001-A AND AMM TASK 23-41-400-001-A , REV 72 DTD 01 AUG 2023.POST INSTALLATION , CARRIED OUT RESISTANCE CHECK FROM TIP TO RETAINER AND BONDING CHECK FROMTHE RETAINER TO THE AIRCRAFT STRUCTURE AS PER AMM TASK 23-61-00-200-001-A REV 72 DTD 01 AUG 2023, FOUND SATISFACTORY. | HMV23/000043/0823/13 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 117 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | MR1090 | 2023-08-26 07:40 | Yes | ct0535 |  | Yes | ct0535 |  | No | [5 empty] | 2023-08-26 07:42 | 2023-08-26 08:42 | 2 | 2023-08-26 10:23 | 2023-08-28 15:33 | 3 | 131 | 131 |  | Hold | Pending Estimates |  |  | 300 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/14 | 35 | DURING DETAILED INSPECTION OF PORTABLE OXYGEN MASK FOUND G1 GALLEY PORTABLE OXYGEN MASK HOSE GOT PINCHED | CARRIED OUT G1 GALLEY PORTABLE OXYGEN MASK REPLACED WITH SERVICEABLE AS PER AMM 35-32-42-000-001 AND AMM TASK 35-32-42-400-001 REV 72 DTD 01 AUG 2023 FOUND SATISFACTORY. | HMV23/000043/0823/14 | Close | Closed | 353000-07-1 | 79 | LINE 2A | Signed Off | DISC- MPD | IRC | Regular | REGULAR | Yes | No | No | No | [5 empty] | CT0535 | 2023-08-28 08:23 | Yes | ct0535 |  | Yes | ct0535 |  | No | [5 empty] | 2023-08-28 08:23 | 2023-08-28 09:23 | 1 | 2023-08-28 08:25 | 2023-08-28 15:31 | 1 | 133 | 133 |  | Hold | Pending Estimates |  |  | 200 | [6 empty] | Hours
No | MIREP | HMV23/000043/0823/15 | 0 | WRT CDLB ENTRY BOOK#11729,S/N:002 COMPARTMENT LATCH 107 BELOW WATER BOILER NOT WORKING ,DEFFERED TO NIGHT HALT /BASE | LATCH 107 OPERATION CHECKED AND FOUND SATISFACTORY | HMV23/000043/0823/15 | Close | Closed | AIRCRAFT ARRIVAL INSPECTION | 117 | LINE 2A | Signed Off | AWR | IRC | Regular | REGULAR | No | No | No | No | [5 empty] | MR1085 | 2023-08-28 17:23 | Yes | MR0049 | B1 | Yes | MR0049 | B1 | No | [5 empty] | 2023-08-24 14:37 | 2023-08-28 18:23 | 5 | 2023-08-28 22:17 | 2023-08-28 22:17 | 1.1 | 135 | 135 |  | Hold | Pending Estimates | [9 empty] | Hours