## Sheet1
DeleteFlag | ATA # | Task # | Seq # | Description | Add New Execution Comments | Previous Execution Comments | Status | Source Task/Discrep. # | Source Tracking # | Work Center # | Sign Off Status | Task Type | Task Category | Job Type | Repair Class. | Exe. Phase | Exec. Category | Part # | Serial # | Position Code | Part Description | Repair Agency | Mech Req? | Mech Sign Off | Insp Req? | Insp Sign Off | RII Req? | RII Sign Off | Addl. Sign Off | Add New Sign Off Comments | Previous Sign Off Comments | Planned Start Date | Planned End Date | Est. Man Hrs. | Actual Start Date | Actual End Date | Actual Man Hrs. | Tracking # | Maint. Manual Ref. # | Long Description | Hold Status | Estimation Status | File Name | Skill # | Zone # | Work Area # | WBS Code | Parent Task # | Root Task # | Workscoping Comments | Message Center
No | 5 | ZL-131-01-1 | 1 | FORWARD CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:51 | 0.52 | 2023-08-24 13:36 | 2023-08-27 12:59 | 1 | 1 |  | FORWARD CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-151-01-1 | 2 | AFT CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:51 | 0.5 | 2023-08-24 13:36 | 2023-08-27 13:02 | 1 | 2 |  | AFT CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-161-01-1 | 3 | BULK CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:51 | 0.5 | 2023-08-24 13:36 | 2023-08-27 16:06 | 1 | 3 |  | BULK CARGO COMPARTMENT GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-195-01-1 | 4 | HYDRAULIC COMPARTMENT AND FAIRINGS GENERAL VISUAL INSPECTION OF HYDRAULIC COMPARTMENT AND FAIRINGS (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:04 | 1.01 | 2023-08-24 13:36 | 2023-08-26 13:12 | 1.05 | 4 |  | HYDRAULIC COMPARTMENT AND FAIRINGS GENERAL VISUAL INSPECTION OF HYDRAULIC COMPARTMENT AND FAIRINGS (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-200-02-3 | 5 | UPPER HALF OF FUSELAGE GENERAL VISUAL INSPECTION OF UPPER HALF OF FUSELAGE |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | ct0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-25 01:14 | 24.38 | 2023-08-24 13:36 | 2023-08-27 12:10 | 2 | 5 |  | UPPER HALF OF FUSELAGE GENERAL VISUAL INSPECTION OF UPPER HALF OF FUSELAGE | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-311-01-1 | 6 | AFT FUSELAGE TAIL SECTION GENERAL VISUAL INSPECTION OF AFT FUSELAGE TAIL SECTION (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:37 | 2023-08-24 14:52 | 0.57 | 2023-08-24 13:36 | 2023-08-28 11:09 | 2 | 6 |  | AFT FUSELAGE TAIL SECTION GENERAL VISUAL INSPECTION OF AFT FUSELAGE TAIL SECTION (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-313-01-1 | 7 | TAIL CONE APU AIR INTAKE AREA GENERAL VISUAL INSPECTION OF TAIL CONE APU AIR INTAKE AREA (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:37 | 2023-08-24 14:44 | 0.29 | 2023-08-24 13:36 | 2023-08-28 11:09 | 2 | 7 |  | TAIL CONE APU AIR INTAKE AREA GENERAL VISUAL INSPECTION OF TAIL CONE APU AIR INTAKE AREA (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-315-01-1 | 8 | TAIL CONE APU AND ACCESSORY COMPARTMENT GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:37 | 2023-08-24 14:50 | 0.5 | 2023-08-24 13:36 | 2023-08-28 11:09 | 2 | 8 |  | TAIL CONE APU AND ACCESSORY COMPARTMENT GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-325-01-1 | 9 | VERTICAL STABILIZER TRAILING EDGE GENERAL VISUAL INSPECTION OF VERTICAL STABILIZER TRAILING EDGE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:54 | 0.64 | 2023-08-24 13:36 | 2023-08-28 17:09 | 3 | 9 |  | VERTICAL STABILIZER TRAILING EDGE GENERAL VISUAL INSPECTION OF VERTICAL STABILIZER TRAILING EDGE (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-411-01-4 (LH) | 10 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:54 | 2.94 | 2023-08-24 13:36 | 2023-08-27 13:18 | 6 | 10 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-411-01-4 (RH) | 11 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:54 | 2.94 | 2023-08-24 13:36 | 2023-08-27 12:55 | 6 | 11 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-415-02-1 (LH) | 12 | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:14 | 1.4 | 2023-08-24 13:36 | 2023-08-27 13:19 | 4 | 12 |  | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-415-02-1 (RH) | 13 | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:14 | 1.4 | 2023-08-24 13:36 | 2023-08-27 13:01 | 4 | 13 |  | LOWER PYLON GENERAL VISUAL INSPECTION OF PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-437-01-4 (LH) | 14 | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.59 | 2023-08-24 13:36 | 2023-08-27 13:21 | 3 | 14 |  | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-437-01-4 (RH) | 15 | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.59 | 2023-08-24 13:36 | 2023-08-27 12:53 | 3 | 15 |  | FAN COWL GENERAL VISUAL INSPECTION OF FAN COWL (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-471-02-1 (LH) | 16 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:09 | 1.21 | 2023-08-24 13:36 | 2023-08-27 13:20 | 4 | 16 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-471-02-1 (RH) | 17 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:09 | 1.21 | 2023-08-24 13:36 | 2023-08-27 12:54 | 3 | 17 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-475-01-1 (LH) | 18 | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:58 | 0.78 | 2023-08-24 13:36 | 2023-08-27 13:17 | 4 | 18 |  | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-475-01-1 (RH) | 19 | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:58 | 0.78 | 2023-08-24 13:36 | 2023-08-27 13:03 | 2 | 19 |  | PYLON REAR SECONDARY STRUCTURE GENERAL VISUAL INSPECTION OF PYLON REAR SECONDARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-500-03-1 (LH) | 20 | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:57 | 0.75 | 2023-08-24 13:36 | 2023-08-27 16:39 | 5 | 20 |  | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-500-03-1 (RH) | 21 | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:57 | 0.75 | 2023-08-24 13:36 | 2023-08-27 13:02 | 3 | 21 |  | WING UPPER SURFACE GENERAL VISUAL INSPECTION OF WING UPPER SURFACE INCLUDING SLATS, FLAPS AND SPOILERS (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-531-01-1 (LH) | 22 | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:46 | 0.32 | 2023-08-24 13:36 | 2023-08-26 15:05 | 6 | 22 |  | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-531-01-1 (RH) | 23 | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:46 | 0.32 | 2023-08-24 13:36 | 2023-08-27 12:50 | 6 | 23 |  | FLAP TRACK NO 2 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-532-01-1 (LH) | 24 | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:46 | 0.32 | 2023-08-24 13:36 | 2023-08-27 13:09 | 5 | 24 |  | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-532-01-1 (RH) | 25 | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:37 | 2023-08-24 14:45 | 0.32 | 2023-08-24 13:36 | 2023-08-27 12:56 | 2 | 25 |  | FLAP TRACK NO 3 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-533-01-1 (LH) | 26 | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:46 | 0.32 | 2023-08-24 13:36 | 2023-08-27 13:06 | 6 | 26 |  | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-533-01-1 (RH) | 27 | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:46 | 0.32 | 2023-08-24 13:36 | 2023-08-27 12:51 | 6 | 27 |  | FLAP TRACK NO 4 AND FAIRING GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-535-01-2 (LH) | 28 | FLAP TAB HINGE AND FAIRING NO. 1A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1A (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:03 | 0.98 | 2023-08-24 13:36 | 2023-08-27 13:08 | 5 | 28 |  | FLAP TAB HINGE AND FAIRING NO. 1A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1A (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-535-01-2 (RH) | 29 | FLAP TAB HINGE AND FAIRING NO. 1A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1A (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:03 | 0.98 | 2023-08-24 13:36 | 2023-08-27 12:58 | 3 | 29 |  | FLAP TAB HINGE AND FAIRING NO. 1A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1A (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-536-01-1 (LH) | 30 | FLAP TAB HINGE AND FAIRING NO. 1B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1B (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 13:19 | 3 | 30 |  | FLAP TAB HINGE AND FAIRING NO. 1B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1B (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-536-01-1 (RH) | 31 | FLAP TAB HINGE AND FAIRING NO. 1B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1B (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 12:48 | 3 | 31 |  | FLAP TAB HINGE AND FAIRING NO. 1B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 1B (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-537-01-2 (LH) | 32 | FLAP TAB HINGE AND FAIRING NO. 3A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3A (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 13:06 | 5 | 32 |  | FLAP TAB HINGE AND FAIRING NO. 3A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3A (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-537-01-2 (RH) | 33 | FLAP TAB HINGE AND FAIRING NO. 3A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3A (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 13:06 | 2 | 33 |  | FLAP TAB HINGE AND FAIRING NO. 3A GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3A (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-538-01-2 (LH) | 34 | FLAP TAB HINGE AND FAIRING NO. 3B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3B (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 13:08 | 5 | 34 |  | FLAP TAB HINGE AND FAIRING NO. 3B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3B (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-538-01-2 (RH) | 35 | FLAP TAB HINGE AND FAIRING NO. 3B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3B (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 13:00 | 2 | 35 |  | FLAP TAB HINGE AND FAIRING NO. 3B GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3B (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-539-01-2 (LH) | 36 | FLAP TAB HINGE AND FAIRING NO. 3C GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3C (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 16:39 | 5 | 36 |  | FLAP TAB HINGE AND FAIRING NO. 3C GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3C (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-539-01-2 (RH) | 37 | FLAP TAB HINGE AND FAIRING NO. 3C GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3C (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 0.57 | 2023-08-24 13:36 | 2023-08-27 12:52 | 4 | 37 |  | FLAP TAB HINGE AND FAIRING NO. 3C GENERAL VISUAL INSPECTION OF FLAP TAB HINGE AND FAIRING NO. 3C (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-573-01-1 (LH) | 38 | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:45 | 0.27 | 2023-08-24 13:36 | 2023-08-26 15:04 | 5 | 38 |  | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-573-01-1 (RH) | 39 | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:45 | 0.27 | 2023-08-24 13:36 | 2023-08-27 12:59 | 2 | 39 |  | INBOARD FIXED TRAILING EDGE STRUCTURE GENERAL VISUAL INSPECTION OF INBOARD FIXED TRAILING EDGE STRUCTURE FROM SHROUD BOX TO RIB 9 (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-574-01-1 (LH) | 40 | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:52 | 0.55 | 2023-08-24 13:36 | 2023-08-27 13:07 | 5 | 40 |  | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-574-01-1 (RH) | 41 | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:52 | 0.55 | 2023-08-24 13:36 | 2023-08-27 14:34 | 5 | 41 |  | FALSE SPAR BO= GENERAL VISUAL INSPECTION OF FALSE SPAR BOX (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-590-01-1 (LH) | 42 | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:48 | 0.4 | 2023-08-24 13:36 | 2023-08-27 13:13 | 4 | 42 |  | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 5 | ZL-590-01-1 (RH) | 43 | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:48 | 0.4 | 2023-08-24 13:36 | 2023-08-27 13:04 | 3 | 43 |  | AILERON GENERAL VISUAL INSPECTION OF AILERON (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 24 | 200002-01-1 | 44 | HIRF/LIGHTNING PROTECTION-THS T/E GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE FOLLOWING HARNESSES: - 405VB, 406VB, 407VB, 408VB, 409VB, LH SI |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:32 | 2.07 | 2023-08-24 13:36 | 2023-08-27 12:33 | 8 | 44 |  | HIRF/LIGHTNING PROTECTION-THS T/E GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE FOLLOWING HARNESSES: - 405VB, 406VB, 407VB, 408VB, 409VB, LH SIDE - 400VB, 401VB, 402VB, 403VB, 404VB, RH SIDE | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 24 | 200121-01-1 | 45 | FORWARD AVIONIC COMPARTMENT CLEANING OF EWIS INSTALLED IN THE FORWARD AVIONIC COMPARTMENT (ONLY IF CONTAMINATED)(EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | RST | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0535 | Yes | CT0535 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:23 | 1.72 | 2023-08-24 13:36 | 2023-08-27 16:30 | 2.5 | 45 |  | FORWARD AVIONIC COMPARTMENT CLEANING OF EWIS INSTALLED IN THE FORWARD AVIONIC COMPARTMENT (ONLY IF CONTAMINATED)(EWIS) | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 24 | 200413-04-1 (LH) | 46 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0535 | Yes | CT0535 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:59 | 3.12 | 2023-08-24 13:36 | 2023-08-26 14:09 | 3.5 | 46 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 24 | 200413-04-1 (RH) | 47 | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:59 | 3.12 | 2023-08-24 13:36 | 2023-08-26 14:49 | 3 | 47 |  | UPPER FORWARD PYLON GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE UPPER FORWARD PYLON (EWIS) | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 24 | 200415-01-1 (LH) | 48 | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0535 | Yes | CT0535 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:14 | 1.4 | 2023-08-24 13:36 | 2023-08-26 14:14 | 2 | 48 |  | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 24 | 200415-01-1 (RH) | 49 | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:14 | 1.4 | 2023-08-24 13:36 | 2023-08-26 14:46 | 3 | 49 |  | PYLON PRIMARY STRUCTURE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON PRIMARY STRUCTURE (EWIS) | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 24 | 200471-01-1 (LH) | 50 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0535 | Yes | CT0535 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:15 | 1.44 | 2023-08-24 13:36 | 2023-08-26 14:07 | 2 | 50 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 24 | 200471-01-1 (RH) | 51 | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:15 | 1.44 | 2023-08-24 13:36 | 2023-08-26 14:47 | 3 | 51 |  | PYLON TO WING LEADING EDGE GENERAL VISUAL INSPECTION OF EWIS INSTALLED IN THE PYLON TO WING LEADING EDGE (EWIS) | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 12 | 212600-09-1 | 52 | AVIONICS EQUIPMENT VENTILATION CLEAN GRID OF RELAY BOX VU PANELS NOTE: DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | RST | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0535 | Yes | CT0535 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:56 | 0.69 | 2023-08-24 13:36 | 2023-08-27 16:19 | 2.5 | 52 |  | AVIONICS EQUIPMENT VENTILATION CLEAN GRID OF RELAY BOX VU PANELS NOTE: DEPENDING ON OPERATING ENVIRONMENT AND OPERATORS EXPERIENCE, A LESS FREQUENT OR MORE FREQUENT INITIAL INTERVAL MAY BE USED. | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 23 | 237100-01-1 | 53 | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF CVR AND CVR-CHANNEL RECORDING |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-08-24 14:37 | 2023-08-24 15:01 | 0.92 | 2023-08-24 13:36 | 2023-08-25 11:16 | 1 | 53 |  | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF CVR AND CVR-CHANNEL RECORDING | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 23 | 237135-02-1 | 54 | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF ULB |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:48 | 0.39 | 2023-08-24 13:36 | 2023-08-28 07:58 | 2 | 54 |  | COCKPIT VOICE RECORDER OPERATIONAL CHECK OF ULB | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 25 | 256535-01-1 | 55 | ELT (REAR FUSELAGE) OPERATIONAL CHECK OF ELT SYSTEM BY MANUAL ACTIVATION |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0535 | Yes | CT0535 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:44 | 0.23 | 2023-08-24 13:36 | 2023-08-25 14:52 | 0.4 | 55 |  | ELT (REAR FUSELAGE) OPERATIONAL CHECK OF ELT SYSTEM BY MANUAL ACTIVATION | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 25 | 256535-04-1 | 56 | ELT (REAR FUSELAGE)- GENERAL VISUAL INSPECTION OF EXTERNAL ELT ANTENNA |  |  | Closed |  |  | LINE 2A | Not Required | MPD | GVI | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 16:08 | 3 | 2023-08-24 13:36 | 2023-08-26 12:18 | 3 | 56 |  | ELT (REAR FUSELAGE)- GENERAL VISUAL INSPECTION OF EXTERNAL ELT ANTENNA | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 25 | 256536-01-1 | 57 | BEACON - LOW FREQUENCY UNDERWATER LOCATOR OPERATIONAL CHECK OF LOW FREQUENCY UNDERWATER LOCATOR BEACON. |  |  | Closed |  |  | LINE 2A | Not Required | MPD | OPC | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:08 | 2.5 | 2023-08-24 13:36 | 2023-08-27 11:50 | 2.5 | 57 |  | BEACON - LOW FREQUENCY UNDERWATER LOCATOR OPERATIONAL CHECK OF LOW FREQUENCY UNDERWATER LOCATOR BEACON. | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 26 | 262541-04-1 | 58 | LAVATORY FIRE EXTINGUISHING VISUAL CHECK OF FIRE EXTINGUISHER BOTTLE PRESSURE READING |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:44 | 0.23 | 2023-08-24 13:36 | 2023-08-26 13:28 | 1 | 58 |  | LAVATORY FIRE EXTINGUISHING VISUAL CHECK OF FIRE EXTINGUISHER BOTTLE PRESSURE READING | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 272100-12-1 | 59 | RUDDER MECHANICAL CONTROL LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | LUB | Aircraft |  | SRV/LUB | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:38 | 1 | 2023-08-24 13:36 | 2023-08-28 10:28 | 2 | 59 |  | RUDDER MECHANICAL CONTROL LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 272145-01-1 | 60 | RUDDER CABLE TENSION REGULATOR FUNCTIONAL CHECK OF TENSION REGULATOR (POINTER WITHIN THE LIMITS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:59 | 0.8 | 2023-08-24 13:36 | 2023-08-27 16:53 | 2 | 60 |  | RUDDER CABLE TENSION REGULATOR FUNCTIONAL CHECK OF TENSION REGULATOR (POINTER WITHIN THE LIMITS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 274142-01-1 | 61 | THS TRIM CTL CABLE TENSION COMPENSATOR FUNCTIONAL CHECK OF POINTER ON TENSION COMPENSATOR (SCALE WITHIN LIMITS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:42 | 0.16 | 2023-08-24 13:36 | 2023-08-27 16:52 | 2 | 61 |  | THS TRIM CTL CABLE TENSION COMPENSATOR FUNCTIONAL CHECK OF POINTER ON TENSION COMPENSATOR (SCALE WITHIN LIMITS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 274451-05-1 | 62 | THS ACTUATOR DETAILED INSPECTION OF UPPER AND LOWER THS ACTUATOR ATTACHMENT (PRIMARY AND SECONDARY) NOTE: FOR NEO A/C ONLY: PLANNING: - ENSURE THAT |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:48 | 0.39 | 2023-08-24 13:36 | 2023-08-26 14:28 | 2 | 62 |  | THS ACTUATOR DETAILED INSPECTION OF UPPER AND LOWER THS ACTUATOR ATTACHMENT (PRIMARY AND SECONDARY) NOTE: FOR NEO A/C ONLY: PLANNING: - ENSURE THAT INSPECTIONS ACCORDING 274451-10-1 AND 274451-11-1 ARE CARRIED OUT PRIOR TO TASK 274451-05-1 (AND PRIOR TO ANY CLEANING), WHEN PLANNED AT THE SAME TIME | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 12 | 275451-01-1 | 63 | FLAP POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | SVC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0049 | Yes | MR0049 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:45 | 0.27 | 2023-08-24 13:36 | 2023-08-27 12:00 | 3 | 63 |  | FLAP POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 278100-03-1 | 64 | SLATS OPERATIONAL CHECK OF WTB/POB |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:50 | 0.46 | 2023-08-24 13:36 | 2023-08-26 07:35 | 2.5 | 64 |  | SLATS OPERATIONAL CHECK OF WTB/POB | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 278100-04-1 (LH) | 65 | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | CHK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:54 | 2.94 | 2023-08-24 13:36 | 2023-08-27 13:18 | 15 | 65 |  | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 278100-04-1 (RH) | 66 | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | CHK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:54 | 2.94 | 2023-08-24 13:36 | 2023-08-27 13:04 | 8 | 66 |  | SLATS CHECK OF SLATS TRANSMISSION SHAFTING INTEGRITY, INCLUDING INSPECTION OF SEAL WITNESS DRAINS | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 12 | 278451-01-1 | 67 | SLAT POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | SVC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0049 | Yes | MR0049 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:45 | 0.27 | 2023-08-24 13:36 | 2023-08-27 12:00 | 3 | 67 |  | SLAT POWER CONTROL UNIT REPLENISH PCU GEARBOX TO CONFIRM FLUID LEVEL | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 28 | 281247-01-1 (LH) | 68 | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:39 | 0.5 | 2023-08-24 13:36 | 2023-08-25 14:34 | 2 | 68 |  | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 28 | 281247-01-1 (RH) | 69 | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:39 | 0.5 | 2023-08-24 13:36 | 2023-08-25 14:32 | 2 | 69 |  | NACA VENT INTAKE VISUAL CHECK OF NACA INTAKE FOR SIGNS OF BLOCKAGE | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 29 | 291000-06-1 | 70 | MAIN HYDRAULIC POWER FUNCTIONAL CHECK OF PTU YELLOW TO GREEN |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:44 | 0.23 | 2023-08-24 13:36 | 2023-08-26 07:34 | 1.5 | 70 |  | MAIN HYDRAULIC POWER FUNCTIONAL CHECK OF PTU YELLOW TO GREEN | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 29 | 291000-20-1 | 71 | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF EDP DEPESSURIZATION |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:37 | 2023-08-24 14:52 | 0.57 | 2023-08-24 13:36 | 2023-08-26 07:31 | 2 | 71 |  | MAIN/AUXILIARY POWER OPERATIONAL CHECK OF EDP DEPESSURIZATION | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 31 | 313300-03-1 | 72 | DFDR SYSTEM INTERCONNECTION OPERATIONAL CHECK OF ULB |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1090 | Yes | MR1090 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:48 | 0.39 | 2023-08-24 13:36 | 2023-08-28 07:58 | 2 | 72 |  | DFDR SYSTEM INTERCONNECTION OPERATIONAL CHECK OF ULB | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 32 | 321113-04-1 (LH) | 73 | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE |  |  | Closed |  |  | LINE 2A | Not Required | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:26 | 1.84 | 2023-08-24 13:36 | 2023-08-27 16:34 | 6 | 73 |  | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE | Hold | Pending Estimates |  |  |  |  | TASK
No | 32 | 321113-04-1 (RH) | 74 | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE |  |  | Closed |  |  | LINE 2A | Not Required | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:37 | 2023-08-24 15:25 | 1.84 | 2023-08-24 13:36 | 2023-08-27 16:35 | 6 | 74 |  | MAIN LANDING GEAR SHOCK ABSORBER FUNCTIONAL CHECK OF MLG SHOCK ABSORBER CHARGE PRESSURE | Hold | Pending Estimates |  |  |  |  | TASK
No | 32 | 323100-05-1 | 75 | NORMAL EXTENSION AND RETRACTION DETAILED INSPECTION OF NOSE GEAR DOOR OPERATING MECHANISM |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:58 | 0.78 | 2023-08-24 13:36 | 2023-08-27 16:04 | 1.5 | 75 |  | NORMAL EXTENSION AND RETRACTION DETAILED INSPECTION OF NOSE GEAR DOOR OPERATING MECHANISM | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 32 | 324000-14-1 | 76 | WHEELS AND BRAKES FUNCTIONAL CHECK OF THE AUTOMATIC REACTIVATION OF THE NORMAL BRAKING MODE (PARKING BRAKE APPLIED) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 19:14 | 10.58 | 2023-08-24 13:36 | 2023-08-26 07:34 | 1.5 | 76 |  | WHEELS AND BRAKES FUNCTIONAL CHECK OF THE AUTOMATIC REACTIVATION OF THE NORMAL BRAKING MODE (PARKING BRAKE APPLIED) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 32 | 324500-01-2 | 77 | PARKING/ULTIMATE EMERGENCY BRAKING SYSTEM OPERATIONAL CHECK OF THE PARKING BRAKE SYSTEM |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:26 | 1.84 | 2023-08-24 13:36 | 2023-08-26 07:36 | 2 | 77 |  | PARKING/ULTIMATE EMERGENCY BRAKING SYSTEM OPERATIONAL CHECK OF THE PARKING BRAKE SYSTEM | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 34 | 341300-13-1 | 78 | Functional Test of the ADM Accuracy |  |  | Closed |  |  | LINE 2A | Not Required | MPD | FNC | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:58 | 0.85 | 2023-08-24 13:36 | 2023-08-26 14:52 | 12 | 78 |  | Functional Test of the ADM Accuracy | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 35 | 353000-07-1 | 79 | PORTABLE OXYGEN DETAILED INSPECTION OF PORTABLE OXYGEN MASK |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0535 | Yes | CT0535 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:50 | 0.46 | 2023-08-24 13:36 | 2023-08-28 16:13 | 1.5 | 79 |  | PORTABLE OXYGEN DETAILED INSPECTION OF PORTABLE OXYGEN MASK | Hold | Pending Estimates |  | B2 |  |  | TASK
No | 49 | 491300-B1-1 | 80 | FIRE SEALS GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS: - COMPARTMENT DOORS - FWD AND AFT FIRE WALLS - SIDE FIRE WALLS - UP |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 16:04 | 3.31 | 2023-08-24 13:36 | 2023-08-26 14:25 | 4 | 80 |  | FIRE SEALS GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS: - COMPARTMENT DOORS - FWD AND AFT FIRE WALLS - SIDE FIRE WALLS - UPPER FIRE WALL | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 49 | 491600-B1-1 | 81 | AIR INTAKE SYSTEM DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:59 | 0.8 | 2023-08-24 13:36 | 2023-08-26 14:23 | 2 | 81 |  | AIR INTAKE SYSTEM DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 49 | 498000-B1-1 | 82 | EXHAUST GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:45 | 0.27 | 2023-08-24 13:36 | 2023-08-26 14:26 | 3 | 82 |  | EXHAUST GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 52 | 521000-02-1 | 83 | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF DOOR SUSPENSION |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:04 | 1.01 | 2023-08-24 13:36 | 2023-08-27 12:11 | 2 | 83 |  | PASSENGER/CREW DOOR FUNCTIONAL CHECK OF DOOR SUSPENSION | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 52 | 521000-03-1 | 84 | PASSENGER/CREW DOOR DETAILED INSPECTION OF DOOR SEALS NOTE: PLANNING: - TASK IS NOT APPLICABLE FOR DEACTIVATED PASSENGER/ CREW DOORS. |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0049 | Yes | MR0049 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:54 | 0.64 | 2023-08-24 13:36 | 2023-08-27 12:00 | 2 | 84 |  | PASSENGER/CREW DOOR DETAILED INSPECTION OF DOOR SEALS NOTE: PLANNING: - TASK IS NOT APPLICABLE FOR DEACTIVATED PASSENGER/ CREW DOORS. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 52 | 521000-04-1 | 85 | PASSENGER/CREW DOOR DETAILED INSPECTION OF PASSENGER/CREW DOOR FOR INTEGRITY AND GOOD ADJUSTMENT OF MECHANISMS (INCLUDING GIRT BAR) NOTE: PLANNING: |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | DET | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:53 | 2.89 | 2023-08-24 13:36 | 2023-08-28 12:36 | 6 | 85 |  | PASSENGER/CREW DOOR DETAILED INSPECTION OF PASSENGER/CREW DOOR FOR INTEGRITY AND GOOD ADJUSTMENT OF MECHANISMS (INCLUDING GIRT BAR) NOTE: PLANNING: - ONLY FWD DOORS FOR POST 37807 (IF AFT DOORS FULLY DEACTIVATED). | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 12 | 521121-02-1 | 86 | PASSENGER / CREW DOOR LUBRICATION OF SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM NOTE: TASK IS NOT APPLICABLE FOR DEACTIVATED PASSE |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | LUB | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:21 | 1.65 | 2023-08-24 13:36 | 2023-08-28 12:35 | 6 | 86 |  | PASSENGER / CREW DOOR LUBRICATION OF SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM NOTE: TASK IS NOT APPLICABLE FOR DEACTIVATED PASSENGER/CREW DOORS | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 52 | 522101-01-1 | 87 | AUTOMATIC OVERWING EMERGENCY EXIT DOOR OPERATIONAL CHECK OF EMERGENCY OVERWING DOOR MECHANISMS |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 17:50 | 7.36 | 2023-08-24 13:36 | 2023-08-27 12:13 | 2 | 87 |  | AUTOMATIC OVERWING EMERGENCY EXIT DOOR OPERATIONAL CHECK OF EMERGENCY OVERWING DOOR MECHANISMS | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 52 | 522101-02-2 | 88 | AUTOMATIC OVERWING EMERGENCY EXIT DOOR OPERATIONAL CHECK OF ESCAPE SLIDE RELEASE MECHANISM |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:26 | 1.84 | 2023-08-24 13:36 | 2023-08-27 12:15 | 2 | 88 |  | AUTOMATIC OVERWING EMERGENCY EXIT DOOR OPERATIONAL CHECK OF ESCAPE SLIDE RELEASE MECHANISM | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 52 | 522101-03-1 | 89 | AUTOMATIC OVERWING EMERGENCY EXIT DOOR FUNCTIONAL CHECK OF FLIGHT LOCK MECHANISM |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:26 | 1.84 | 2023-08-24 13:36 | 2023-08-25 14:36 | 2.5 | 89 |  | AUTOMATIC OVERWING EMERGENCY EXIT DOOR FUNCTIONAL CHECK OF FLIGHT LOCK MECHANISM | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 12 | 524100-02-1 | 90 | ACCESS DOORS LUBRICATION OF EXTERIOR AVIONIC COMPARTMENT DOOR HANDLE |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | LUB | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:55 | 0.66 | 2023-08-24 13:36 | 2023-08-27 11:47 | 1.2 | 90 |  | ACCESS DOORS LUBRICATION OF EXTERIOR AVIONIC COMPARTMENT DOOR HANDLE | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 531151-02-1 | 91 | DOOR STOP FITTINGS DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. |  |  | Closed |  |  | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 16:44 | 2.1 | 2023-08-24 13:36 | 2023-08-26 13:30 | 1 | 91 |  | DOOR STOP FITTINGS DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 531176-02-1 | 92 | COCKPIT SIDE WINDOWS FRAMEWORK GENERAL VISUAL INSPECTION OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH |  |  | Closed |  |  | LINE 2A | Not Required | MPD | GVI | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 1 | 2023-08-24 13:36 | 2023-08-26 14:48 | 2 | 92 |  | COCKPIT SIDE WINDOWS FRAMEWORK GENERAL VISUAL INSPECTION OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 531178-02-1 | 93 | COCKPIT WINDSHIELD RETAINERS GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. |  |  | Closed |  |  | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:53 | 1 | 2023-08-24 13:36 | 2023-08-26 14:47 | 2 | 93 |  | COCKPIT WINDSHIELD RETAINERS GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 531182-02-1 | 94 | WINDSHIELD SLIDING WINDOW FRAME DETAILED INSPECTION OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 AND FR8 FRAMES, INTERNAL STRUCTURE FROM |  |  | Closed |  |  | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-25 00:45 | 10.12 | 2023-08-24 13:36 | 2023-08-27 12:25 | 2 | 94 |  | WINDSHIELD SLIDING WINDOW FRAME DETAILED INSPECTION OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 AND FR8 FRAMES, INTERNAL STRUCTURE FROM FR4 TO FR8 LH/RH. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 531900-03-1 | 95 | FUSELAGE DRAINAGE OPERATIONAL CHECK OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL FROM OUTSIDE |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:14 | 1.38 | 2023-08-24 13:36 | 2023-08-25 14:57 | 1.5 | 95 |  | FUSELAGE DRAINAGE OPERATIONAL CHECK OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL FROM OUTSIDE | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 533900-01-1 | 96 | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE HOLES IN PRESSURE FLOOR FROM MLG BAY |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:44 | 0.23 | 2023-08-24 13:36 | 2023-08-27 11:34 | 0.5 | 96 |  | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE HOLES IN PRESSURE FLOOR FROM MLG BAY | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 534134-02-1 | 97 | DOOR STOP FITTINGS FR 66 AND 68 DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND FRAME 68, LH/RH |  |  | Closed |  |  | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:59 | 1.35 | 2023-08-24 13:36 | 2023-08-26 13:32 | 1 | 97 |  | DOOR STOP FITTINGS FR 66 AND 68 DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND FRAME 68, LH/RH. | Hold | Pending Estimates |  |  |  |  | TASK
No | 53 | 535900-02-1 | 98 | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE AT BULK CARGO COMPARTMENT DOOR FROM OUTSIDE |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | OPC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:44 | 0.23 | 2023-08-24 13:36 | 2023-08-25 14:24 | 0.5 | 98 |  | FUSELAGE DRAINAGE OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE AT BULK CARGO COMPARTMENT DOOR FROM OUTSIDE | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 54 | 545900-W1-1 (LH) | 99 | PYLON DRAINAGE VISUAL CHECK OF PYLON DRAINAGE SYSTEM IN ZONE C. |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:38 | 2.32 | 2023-08-24 13:36 | 2023-08-27 13:12 | 4 | 99 |  | PYLON DRAINAGE VISUAL CHECK OF PYLON DRAINAGE SYSTEM IN ZONE C. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 54 | 545900-W1-1 (RH) | 100 | PYLON DRAINAGE VISUAL CHECK OF PYLON DRAINAGE SYSTEM IN ZONE C. |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | VCK | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:38 | 2.32 | 2023-08-24 13:36 | 2023-08-27 13:05 | 4 | 100 |  | PYLON DRAINAGE VISUAL CHECK OF PYLON DRAINAGE SYSTEM IN ZONE C. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 12 | 561200-02-1 | 101 | SLIDING WINDOWS LUBRICATION OF COCKPIT SLIDING WINDOW TRACKS |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | LUB | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 14:50 | 0.46 | 2023-08-24 13:36 | 2023-08-26 13:35 | 2 | 101 |  | SLIDING WINDOWS LUBRICATION OF COCKPIT SLIDING WINDOW TRACKS | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 78 | 783200-W6-1 (LH) | 102 | THRUST REVERSER HALVES FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION. |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR0218 | Yes | MR0218 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:06 | 1.08 | 2023-08-24 13:36 | 2023-08-25 14:34 | 3 | 102 |  | THRUST REVERSER HALVES FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 78 | 783200-W6-1 (RH) | 103 | THRUST REVERSER HALVES FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION. |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | FNC | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:06 | 1.08 | 2023-08-24 13:36 | 2023-08-26 08:09 | 3 | 103 |  | THRUST REVERSER HALVES FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 27 | 2001-16-09 | 104 | FLIGHT CONTROLS - ELEVATOR BACKLASH - INSPECTION |  |  | Closed |  |  | LINE 2A | Signed Off | AD | MAINT | Aircraft |  | INSP | REGULAR | [5 empty] | Yes | mr0208 | Yes | mr0208 | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 16:08 | 2.76 | 2023-08-24 13:36 | 2023-08-26 11:00 | 3.5 | 104 |  | FLIGHT CONTROLS - ELEVATOR BACKLASH - INSPECTION | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 20 | WEAR LIMITS- BONDING LEADS | 105 | WEAR LIMITS ALLOWED FOR BONDING LEADS |  |  | Closed |  |  | LINE 2A | Not Required | INT | VCK | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:38 | 3 | 2023-08-24 13:36 | 2023-08-28 16:08 | 20 | 105 |  | CARRY OUT VISUAL INSPECTION TO DETERMINE WEAR LIMITS ALLOWED FOR BONDING LEADS FITTED ON MOVABLE SURFACES | Not in hold | Not Required |  | B2 |  |  | TASK
No | 20 | AGING OF CIRCUIT BREAKERS | 106 | AGING OF CIRCUIT BREAKERS |  |  | Closed |  |  | LINE 2A | Not Required | INT | MAINT | Aircraft |  | POWER OFF | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:38 | 2023-08-24 15:38 | 2 | 2023-08-24 13:36 | 2023-08-27 12:28 | 2 | 106 | 240000-200-004 | PERFORM A MANUAL CYCLING OF ALL THERMAL CIRCUIT BREAKERS ON AND OFF (WITHOUT ANY LOAD) AS PER AMM 240000-200-004 | Not in hold | Not Required |  | B2 |  |  | TASK
No | 52 | 522101-07-1 | 107 | AUTOMATIC OVERWING EMERGENCY EXIT DOOR DETAILED INSPECTION OF EMERGENCY OVERWING DOOR SEALS. |  |  | Closed |  |  | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:47 | 2023-08-25 00:47 | 10 | 2023-08-24 13:44 | 2023-08-26 14:48 | 2 | 107 |  | AUTOMATIC OVERWING EMERGENCY EXIT DOOR DETAILED INSPECTION OF EMERGENCY OVERWING DOOR SEALS. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 52 | 522101-08-1 | 108 | AUTOMATIC OVERWING EMERGENCY EXIT DOOR DETAILED INSPECTION OF THE ROD ASSEMBLY AND LATCH MECHANISM. |  |  | Closed |  |  | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:47 | 2023-08-25 00:47 | 10 | 2023-08-24 13:44 | 2023-08-27 12:26 | 2 | 108 |  | AUTOMATIC OVERWING EMERGENCY EXIT DOOR DETAILED INSPECTION OF THE ROD ASSEMBLY AND LATCH MECHANISM. | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 53 | 534190-02-2 | 109 | DOOR STOP FITTINGS ON FR 47.2A & 47.4 DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 47.2A AND FRAME |  |  | Closed |  |  | LINE 2A | Not Required | MPD | DET | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 14:47 | 2023-08-24 15:53 | 1.1 | 2023-08-24 13:47 | 2023-08-26 13:31 | 1 | 109 |  | DOOR STOP FITTINGS ON FR 47.2A & 47.4 DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 47.2A AND FRAME 47.4, LH/RH. | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | ZL-734-01-1 | 110 | MAIN LANDING GEAR MAIN DOORS GENERAL VISUAL INSPECTION OF MAIN LANDING GEAR MAIN DOORS (EWIS) |  |  | Closed |  |  | LINE 2A | Signed Off | MPD | GVI | Aircraft |  | AIRCRAFT JACKING | REGULAR | [5 empty] | Yes | MR1546 | Yes | MR1546 | No |  |  |  |  | 2023-08-24 14:47 | 2023-08-24 15:01 | 0.55 | 2023-08-24 13:47 | 2023-08-26 13:03 | 1 | 110 |  | MAIN LANDING GEAR MAIN DOORS GENERAL VISUAL INSPECTION OF MAIN LANDING GEAR MAIN DOORS (EWIS) | Hold | Pending Estimates |  | B1 |  |  | TASK
No | 51 | AWR23/002554/0823 | 111 | REF TO IGO EO-4278 DENT ON RH SLAT#2 NOSE PART OF TOP SKIN |  | REFER IRC: HMV23/000043/0823/10 FOR RH WING SLAT#2 REPLACEMENT DETAILS. | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:52 | 2023-08-24 15:52 | 1 | 2023-08-24 13:52 | 2023-08-28 17:33 | 2 | 111 |  | REF TO IGO EO-4278 DENT ON RH SLAT#2 NOSE PART OF TOP SKIN | Hold | Pending Estimates |  |  |  |  | TASK
No | 51 | AWR23/002555/0823 | 112 | REF TO IGO EO-4279 DENT ON RH SLAT#2 NOSE PART OF TOP SKIN |  | REFER IRC HMV23/000043/0823/7 FOR SLAT REMOVAL AND HMV23/000043/0823/10 FOR SLAT INSTALLATION. | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR1085 | Yes | MR1085 | No |  |  |  |  | 2023-08-24 14:52 | 2023-08-24 15:52 | 1 | 2023-08-24 13:52 | 2023-08-29 00:51 | 2 | 112 |  | REF TO IGO EO-4279 DENT ON RH SLAT#2 NOSE PART OF TOP SKIN | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | CARPET REPLACEMENT | 113 | CARRY OUT CARPET REPLACEMENT AS PER CUSTOMER REQUEST |  | AISLE CARPET , EMERGENCY ROW CARPET AND MID CABIN ROW CARPET REPLACED AS PER AMM 25-28-41-000-001-A/25-28-41-400-001-A REV72,DT.1 AUG2023 | Closed |  |  | LINE 2A | Not Required | Non Routine | RPL | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 16:26 | 2023-08-24 17:26 | 1 | 2023-08-24 15:19 | 2023-08-28 13:35 | 15 | 113 |  | CARRY OUT CARPET REPLACEMENT AS PER CUSTOMER REQUEST | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | NTF REPLACEMENT | 114 | CARRY OUT REPLACEMENT OF NTF AS PER CUSTOMER REQUEST |  | FWD AND AFT NTF COVERING REPLACED AS PER AMM 25-28-42-000-001-A/ 25-28-42-400-001-A REV72, DT.1 AUG2023 | Closed |  |  | LINE 2A | Not Required | Non Routine | RPL | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 16:26 | 2023-08-24 17:26 | 1 | 2023-08-24 15:19 | 2023-08-28 13:36 | 15 | 114 |  | CARRY OUT REPLACEMENT OF NTF AS PER CUSTOMER REQUEST | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | VINYL REPLACEMENT | 115 | CARRY OUT VINYL REPLACEMENT AS PER CUSTOMER REQUEST |  | CARRIED OUT VINYL REPLACEMENT AS PER AMM25-20-00-340-003-A REV72 DT 01.08.2023 | Closed |  |  | LINE 2A | Not Required | Non Routine | RPL | Aircraft |  |  | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-24 16:26 | 2023-08-24 17:26 | 1 | 2023-08-24 15:19 | 2023-08-28 15:16 | 10 | 115 |  | CARRY OUT VINYL REPLACEMENT AS PER CUSTOMER REQUEST | Hold | Pending Estimates |  |  |  |  | TASK
No | 12 | ISSUE OF COMMERCIAL ITEMS | 116 | ISSUE OF COMMERCIAL ITEMS FOR AIRCRAFT MAINTENANCE |  |  | Closed |  |  | LINE 2A | Not Required | INT | CLN | Aircraft |  | POST DOCK | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-25 07:44 | 2023-08-25 08:14 | 0.5 | 2023-08-25 06:44 | 2023-08-28 17:28 | 5 | 116 |  | ISSUE OF COMMERCIAL ITEMS FOR AIRCRAFT MAINTENANCE | Hold | Pending Estimates |  |  |  |  | TASK
No | 0 | AIRCRAFT ARRIVAL INSPECTION | 117 | AIRCRAFT ARRIVAL INSPECTION |  |  | Closed |  |  | LINE 2A | Not Required | INT | GVI | Aircraft |  | INSP | REGULAR | [5 empty] | No |  | No |  | No |  |  |  |  | 2023-08-25 10:06 | 2023-08-25 11:06 | 2 | 2023-08-25 09:06 | 2023-08-28 22:21 | 3 | 117 |  | CARRY OUT AIRCRAFT ARRIVAL INSPECTION AS PER GAT INSPECTION SCHEDULE | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | AWR23/002577/0823 | 119 | CARRY OUT CABIN REFURBISHMENT |  | REFER IRC HMV23/000043/0823/2 CA SEATS AND DOOR TRIMS PAINTING DETAILS | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | CT0536 | Yes | CT0536 | No |  |  |  |  | 2023-08-25 10:50 | 2023-08-25 11:50 | 1 | 2023-08-25 09:50 | 2023-08-28 16:06 | 2 | 119 |  | CARRY OUT CABIN REFURBISHMENT | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | AWR23/002610/0823 | 132 | CARRY OUT EXTERNAL PAINT TOUCH UP. |  | CARRIED OUT EXTERNAL PAINT TOUCH UP OF AIRCRAFT IN THE FOLLOWING AREAS 1.LH & RH SIDE THS TIP 2. LH & RH SIDE AIR CONDITIONING RAM AIR INLET AND EXHAUST. 3.BELLY FAIRINGS 4.CROWN AREA AS PER SRM 51-75-12-911-002 REV NO.24 DATED:AUG 01/2023.FOUND SATISFACTORY. | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR0263 | Yes | MR0263 | No |  |  |  |  | 2023-08-27 11:12 | 2023-08-27 12:12 | 1 | 2023-08-27 10:12 | 2023-08-28 15:37 | 100 | 132 |  | CARRY OUT EXTERNAL PAINT TOUCH UP. | Hold | Pending Estimates |  |  |  |  | TASK
No | 5 | AWR23/002611/0823 | 134 | AS PER CUSTOMER WORK ORDER, CARRY OUT WEEKLY INSPECTION. |  | AS PER CUSTOMER WORK ORDER, CARRIED OUT WEEKLY INSPECTION AS PER APPROVED SCHEDULE IGO/E&M/APPROVAL/INSP.SCH/178 DATED 16.11.2022 | Closed |  |  | LINE 2A | Signed Off | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes | MR0208 | Yes | MR0208 | No |  |  |  |  | 2023-08-28 10:31 | 2023-08-28 11:31 | 1 | 2023-08-28 09:31 | 2023-08-28 17:41 | 10 | 134 |  | AS PER CUSTOMER WORK ORDER, CARRY OUT WEEKLY INSPECTION. | Hold | Pending Estimates |  |  |  |  | TASK
No | 25 | AWR23/002654/0823 | 136 | CARRY OUT CABIN REFUBRISHMENT |  |  | Pre-Closed |  |  | LINE 2A | Pending Mech&Insp | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes |  | Yes |  | No |  |  |  |  | 2023-08-30 11:59 | 2023-08-30 12:59 | 1 | 2023-08-30 10:59 | 2023-08-30 13:01 | 0 | 136 |  | CARRY OUT CABIN REFUBRISHMENT | Hold | Pending Estimates |  |  |  |  | TASK
No | 51 | AWR23/002655/0823 | 137 | CARRY OUT PAINTING AS PER NEW LIVERY |  |  | Pre-Closed |  |  | LINE 2A | Pending Mech&Insp | Non Routine | ADJ | Aircraft |  | Regular | REGULAR | [5 empty] | Yes |  | Yes |  | No |  |  |  |  | 2023-08-30 12:04 | 2023-08-30 13:04 | 1 | 2023-08-30 11:04 | 2023-08-30 13:02 | 0 | 137 |  | CARRY OUT PAINTING AS PER NEW LIVERY | Hold | Pending Estimates |  |  |  |  | TASK